## Summary
SM Bean — Closed-Beta QA Round 1: Results
Run 27 Sep 2026 on production (sm-bean-production-eb50.up.railway.app) · Chrome desktop + in-app browser mobile emulation · Tester: Claude (acting as QA agency) for Hemant
RECOMMENDATION
Result by status |  |  |  | Bugs not yet fixed, by severity
Status | Tests | % of total |  | Severity | Not fixed
Pass |  |  |  | P0
Fail |  |  |  | P1
Partial |  |  |  | P2
Blocked |  |  |  | P3
Not run |  |  |  | Total
Total
Failures by suite
Suite | Tests | Pass | Fail | Partial | Blocked / Not run
Pre-conditions
Smoke
A. Sign-in
B. Onboarding
C. Org/workspace
D. Social accounts
E. Composer
F. Calendar
G. Approvals/portal
H. CSV import
I. Media library
J. Beta features
K. Permissions
L. Tenant isolation
M. Security
N. Publisher
O. Ops
P. Accessibility
Q. Mobile
R. Public pages
S. Performance
Notes
• Why so many 'Blocked': the plan's pre-conditions were not met (no SMTP, no S3, no test social accounts, PR #1 not deployed). Every email, publishing and role test depends on them.
• Test data created and removed: 1 idea, 1 image, 1 ghost post (all deleted). Rejected uploads left nothing behind.
• Test data created and NOT removable by QA: user account qa-test-noninvited@example.com and its 'My Workspace' (created by the A2 signup test). Please delete it from /admin/.
• Nothing was published to any social platform and no one was invited or emailed.
• Edit the Status column on 'Test Results' and the Status column on 'Bugs' during retest — every number on this page recalculates.

## Test Results
Test ID | Suite | Test | Expected | Priority | Status | Actual result / notes | Bug | Tester | Date | Retest 27 Sep (2 PM IST)
PRE-1 | Pre-conditions | Backup taken, PR #1 merged and deployed to web + worker | Latest code live | P0 | Fail | Last deploy on both services is 24 Sep (commit 566b08c 'fix(auth): CSRF_TRUSTED_ORIGINS'). PR #1 fixes are not live: /terms/, /pricing/, /robots.txt 404; logout still a GET link. | BUG-01 | Claude (QA) | 2026-09-27 | Fail
PRE-2 | Pre-conditions | /health/ returns 200 | 200 | P0 | Pass | 200 {"status":"ok"} in ~0.3 s. |  | Claude (QA) | 2026-09-27 | Pass
PRE-3 | Pre-conditions | SMTP settings set | Email works | P0 | Fail | No EMAIL_*/SMTP variables on the web service. Invites, resets, magic links and failure alerts cannot be sent. | BUG-02 | Claude (QA) | 2026-09-27 | Fail
PRE-4 | Pre-conditions | S3 media storage set | Media on S3 | P0 | Fail | No AWS/S3 variables and no Railway volume. Media is written to the container disk and served from /media/…; it will be lost on the next redeploy. | BUG-03 | Claude (QA) | 2026-09-27 | Fail
PRE-5 | Pre-conditions | Sentry DSN set | Errors captured | P1 | Fail | No SENTRY_DSN on web or worker. | BUG-04 | Claude (QA) | 2026-09-27 | Fail
PRE-6 | Pre-conditions | SUPPORT_EMAIL and WEBHOOK_SECRET set | Set | P1 | Fail | Neither variable exists. | BUG-04 | Claude (QA) | 2026-09-27 | Partial
PRE-7 | Pre-conditions | SIGNUP_ALLOWLIST holds testers; SIGNUP_MODE=invite_only | Invite-only | P0 | Fail | Neither variable exists. Open signup confirmed in A2. | BUG-05 | Claude (QA) | 2026-09-27 | Fail
PRE-8 | Pre-conditions | Worker start command is run_worker, restarted after migrations | run_worker | P0 | Fail | Worker start command is 'python manage.py process_tasks'. | BUG-06 | Claude (QA) | 2026-09-27 | Pass
PRE-9 | Pre-conditions | DJANGO_SUPERUSER_* deleted; pre-deploy no longer resets admin | Removed | P0 | Fail | Both variables still set; pre-deploy command re-creates the superuser and resets its password on every deploy. | BUG-07 | Claude (QA) | 2026-09-27 | Partial
PRE-10 | Pre-conditions | Google sign-in client ID/secret + callback registered | Google works | P0 | Pass | GOOGLE_AUTH_CLIENT_ID/SECRET present; owner signed in. One 'Unauthorized: /accounts/google/login/callback/' seen in logs at 06:14 UTC — retest. |  | Claude (QA) | 2026-09-27
PRE-11 | Pre-conditions | Terms and Privacy pages live with real text | Live | P0 | Fail | /terms/ and /privacy/ return an unbranded 404. | BUG-08 | Claude (QA) | 2026-09-27 | Fail
PRE-12 | Pre-conditions | Test social accounts ready | Connected | P0 | Fail | Workspace has 0 connected accounts. All publishing tests blocked. | BUG-09 | Claude (QA) | 2026-09-27 | Fail
SMK-1 | Smoke | /health/ returns 200 | 200 | P0 | Pass | OK. |  | Claude (QA) | 2026-09-27 | Pass
SMK-2 | Smoke | Google sign-in, allowlisted tester | Lands in app | P0 | Pass | Owner lands on Publish page. See PRE-10 note. |  | Claude (QA) | 2026-09-27
SMK-3 | Smoke | Non-allowlisted account is refused | Invite-only page, no account | P0 | Fail | Email signup with qa-test-noninvited@example.com created an account and workspace instantly, no invite, no email verification. | BUG-05 | Claude (QA) | 2026-09-27 | Fail
SMK-4 | Smoke | Invite email arrives within 2 min | Arrives | P0 | Blocked | No SMTP configured (PRE-3). | BUG-02 | Claude (QA) | 2026-09-27
SMK-5 | Smoke | Password reset email works | Arrives | P0 | Blocked | No SMTP configured. | BUG-02 | Claude (QA) | 2026-09-27
SMK-6 | Smoke | Upload image, reload, still there (S3) | Persists on S3 | P0 | Fail | Image persisted after page reload, but it is stored on local container disk (/media/…), not S3. Will not survive a redeploy. | BUG-03 | Claude (QA) | 2026-09-27 | Fail
SMK-7 | Smoke | Publish now to each ready platform | Published | P0 | Blocked | No connected test accounts. | BUG-09 | Claude (QA) | 2026-09-27
SMK-8 | Smoke | Scheduled post publishes within 1 min | On time | P0 | Blocked | No connected test accounts. | BUG-09 | Claude (QA) | 2026-09-27
SMK-9 | Smoke | Client magic-link approval | Approved | P0 | Blocked | No SMTP, no accounts. | BUG-02 | Claude (QA) | 2026-09-27
SMK-10 | Smoke | Worker restart during due post: exactly once | Once | P0 | Blocked | No accounts; worker on wrong command. | BUG-06 | Claude (QA) | 2026-09-27
SMK-11 | Smoke | 11 wrong passwords in 1 min -> 429 | 429 on 11th | P1 | Pass | Attempts 1-10 returned the error page, 11 and 12 returned 429 'Too many requests'. |  | Claude (QA) | 2026-09-27
SMK-12 | Smoke | Sentry shows test error | Visible | P1 | Blocked | Sentry not configured. | BUG-04 | Claude (QA) | 2026-09-27
A1 | A. Sign-in | New allowlisted user, Google | Onboarding | P0 | Blocked | Needs an allowlist (PRE-7) and a fresh Google test account. |  | Claude (QA) | 2026-09-27
A2 | A. Sign-in | Non-allowlisted, not invited user signs up | Invite-only page, no account | P0 | Fail | Email signup open to anyone; account + 'My Workspace' created at once. | BUG-05 | Claude (QA) | 2026-09-27 | Fail
A3 | A. Sign-in | Invite link, then Google | Joins with role | P0 | Blocked | No SMTP. | BUG-02 | Claude (QA) | 2026-09-27
A4 | A. Sign-in | Existing user signs in with Google again | Same account | P0 | Pass | Owner account re-used (single member in org). Retest after callback 401 in logs. |  | Claude (QA) | 2026-09-27
A5 | A. Sign-in | Email user later uses Google, same email | Same account | P1 | Not run | Needs a second tester Google account. |  | Claude (QA) | 2026-09-27
A6 | A. Sign-in | Wrong then right password | Error, then success | P0 | Partial | Wrong password shows error. Right password not entered by QA (policy). |  | Claude (QA) | 2026-09-27
A7 | A. Sign-in | Password reset end to end | Works once | P0 | Blocked | No SMTP. | BUG-02 | Claude (QA) | 2026-09-27
A8 | A. Sign-in | 11 wrong passwords in 60 s | 429 | P1 | Pass | 429 from attempt 11. |  | Claude (QA) | 2026-09-27
A9 | A. Sign-in | Log out is a POST button | POST | P1 | Fail | Sidebar 'Log out' is a plain link to /accounts/logout/ (GET). | BUG-10 | Claude (QA) | 2026-09-27 | Fail
A10 | A. Sign-in | GET /accounts/logout/ does not log out | Stays signed in | P2 | Fail | Visiting the URL signed the owner out immediately (reproduced twice, two browsers). | BUG-10 | Claude (QA) | 2026-09-27
A11 | A. Sign-in | Cancel on Google consent | Clear message | P2 | Not run |  |  | Claude (QA) | 2026-09-27
B1 | B. Onboarding | First login shows 4-item checklist | Checklist | P1 | Fail | No checklist on the owner dashboard; new signup lands straight on Publish with a 'Welcome — connect a channel' empty state. | BUG-11 | Claude (QA) | 2026-09-27 | Fail
B2 | B. Onboarding | Items tick as completed | Ticks | P1 | Blocked | Depends on B1. |  | Claude (QA) | 2026-09-27
B3 | B. Onboarding | Dismiss persists | Hidden | P2 | Blocked | Depends on B1. |  | Claude (QA) | 2026-09-27
C1 | C. Org/workspace | Create second workspace, data separate | Separate | P0 | Not run | Not approved to create workspaces in production. |  | Claude (QA) | 2026-09-27
C2 | C. Org/workspace | Invite one user per role | Right role | P0 | Blocked | No SMTP. | BUG-02 | Claude (QA) | 2026-09-27
C3 | C. Org/workspace | Change role, remove member | Immediate | P1 | Blocked | Only one member. |  | Claude (QA) | 2026-09-27
C4 | C. Org/workspace | Client cannot open /members/ | Blocked | P1 | Blocked | No client user. |  | Claude (QA) | 2026-09-27
C5 | C. Org/workspace | Resend/revoke invite | Revoked link dead | P2 | Blocked | No SMTP. |  | Claude (QA) | 2026-09-27
C6 | C. Org/workspace | Timezone + approval mode saved and obeyed | Obeyed | P1 | Partial | Approvals page shows the 4 modes clearly. Save/behaviour not tested (no accounts). Timezone label says 'Calcutta' — use 'Kolkata'. | BUG-27 | Claude (QA) | 2026-09-27
D1 | D. Social accounts | Connect each ready platform | Connected | P0 | Blocked | No test accounts provided. | BUG-09 | Claude (QA) | 2026-09-27
D2 | D. Social accounts | Connect same account twice | No duplicate | P2 | Blocked |  |  | Claude (QA) | 2026-09-27
D3 | D. Social accounts | Disconnect account with scheduled posts | Posts to Draft + notice | P0 | Blocked |  |  | Claude (QA) | 2026-09-27
D4 | D. Social accounts | Remove only on disconnected | Confirmed | P1 | Blocked |  |  | Claude (QA) | 2026-09-27
D5 | D. Social accounts | Platform-side revoke | Fails once, needs reconnect | P0 | Blocked |  |  | Claude (QA) | 2026-09-27
D6 | D. Social accounts | Reconnect | Connected | P1 | Blocked |  |  | Claude (QA) | 2026-09-27
D7 | D. Social accounts | LinkedIn/TikTok/Pinterest hidden or labelled | Clear state | P1 | Fail | Connect page greys them out as 'Not Configured' (OK), but the sidebar 'CONNECT CHANNELS' block promotes 'LinkedIn (Company Page)' and 'TikTok' as the first things to connect. | BUG-12 | Claude (QA) | 2026-09-27 | Fail
E1 | E. Composer | Save draft with text only | Appears in Drafts | P0 | Fail | With no account selected, Save Draft POST returns 204, redirects to Publish, shows no message, and nothing is saved. Drafts shows '0 drafts'. User text is lost silently. | BUG-13 | Claude (QA) | 2026-09-27 | Fail
E2 | E. Composer | Schedule to 2 accounts | On time | P0 | Blocked | No accounts. |  | Claude (QA) | 2026-09-27
E3 | E. Composer | Publish now | Live < 1 min | P0 | Blocked | No accounts. |  | Claude (QA) | 2026-09-27
E4 | E. Composer | Zero accounts selected | Rejected with message + link; no ghost post | P0 | Fail | No message (see E1). 'Create Post' from an Idea creates a post record that never appears in Drafts/Queue (ghost post, reachable only by URL). | BUG-14 | Claude (QA) | 2026-09-27 | Fail
E5 | E. Composer | Past time rejected | Message | P1 | Blocked |  |  | Claude (QA) | 2026-09-27
E6 | E. Composer | Character limit warning | Warns | P1 | Blocked | Preview needs a platform. |  | Claude (QA) | 2026-09-27
E7 | E. Composer | Upload JPG/PNG/MP4, remove one | Progress; removed not attached | P0 | Partial | PNG upload via media library works and persists. Composer attach/remove not tested (cannot save a post). |  | Claude (QA) | 2026-09-27
E8 | E. Composer | Oversized file and fake .jpg | Rejected with message | P1 | Fail | Fake .jpg, SVG-with-script and HTML-renamed-.png were all rejected (good) but the server answers 200 with an empty body and the page reloads: the user never learns why the file vanished. | BUG-15 | Claude (QA) | 2026-09-27 | Fail
E9 | E. Composer | Unsplash import with attribution | Attached | P2 | Not run |  |  | Claude (QA) | 2026-09-27
E10 | E. Composer | Save as template / use template | Pre-filled | P2 | Not run |  |  | Claude (QA) | 2026-09-27
E11 | E. Composer | Tags and categories filter | Filters | P2 | Not run | Plan link /tags/ returns raw JSON '[]' in the browser — no tag management page at that URL. | BUG-26 | Claude (QA) | 2026-09-27
E12 | E. Composer | Edit scheduled post | Publishes once | P0 | Blocked |  |  | Claude (QA) | 2026-09-27
E13 | E. Composer | Clone and delete | Independent | P1 | Partial | Delete works with a clear confirm modal. Clone not tested. |  | Claude (QA) | 2026-09-27
E14 | E. Composer | Form error keeps text | Kept | P1 | Fail | Covered by E1: text discarded with no error. | BUG-13 | Claude (QA) | 2026-09-27 | Fail
E15 | E. Composer | Autosave recovers text | Recovered | P2 | Partial | After 4 s of idle the footer still read 'Not saved yet'. Retest with a longer wait and a connected account. |  | Claude (QA) | 2026-09-27
E16 | E. Composer | Ideas board create/move/convert | Linked | P2 | Partial | Create, drag to 'To Do' and persistence work; XSS escaped. 'Create Post' drops the idea title (only the body is copied) and the post is invisible (E4). | BUG-14 | Claude (QA) | 2026-09-27
F1 | F. Calendar | Month/week/list in workspace tz | Correct | P0 | Partial | Month grid renders (workspace + org calendar). First click on 'Calendar' toggle did nothing; second worked. Could not verify placement (no posts). | BUG-20 | Claude (QA) | 2026-09-27
F2 | F. Calendar | Drag to reschedule | New time | P0 | Blocked |  |  | Claude (QA) | 2026-09-27
F3 | F. Calendar | Concurrent drag -> 409 | 409 message | P1 | Blocked |  |  | Claude (QA) | 2026-09-27
F4 | F. Calendar | Recurring post | Each once | P1 | Blocked |  |  | Claude (QA) | 2026-09-27
F5 | F. Calendar | Calendar events CRUD | Valid | P2 | Not run |  |  | Claude (QA) | 2026-09-27
F6 | F. Calendar | Bulk delete mix | Skips published | P1 | Blocked |  |  | Claude (QA) | 2026-09-27
F7 | F. Calendar | Slots and queues | Next slots | P2 | Not run | Pages load (200). |  | Claude (QA) | 2026-09-27
F8 | F. Calendar | Queue/Drafts/Approvals/Sent tabs | Right posts | P1 | Fail | With no channel connected every tab shows the same 'Welcome — Connect a channel' empty state, so Drafts cannot be reached from Publish. | BUG-20 | Claude (QA) | 2026-09-27 | Fail
G1 | G. Approvals/portal | Contributor submits (internal) | Pending review | P0 | Blocked | Needs a contributor user (SMTP). |  | Claude (QA) | 2026-09-27
G2 | G. Approvals/portal | Manager approve/changes/reject | Status + notify | P0 | Blocked |  |  | Claude (QA) | 2026-09-27
G3 | G. Approvals/portal | Client magic-link email | Opens portal | P0 | Blocked | No SMTP. | BUG-02 | Claude (QA) | 2026-09-27
G4 | G. Approvals/portal | Client approve/reject/hold | Held doesn't publish | P0 | Blocked |  |  | Claude (QA) | 2026-09-27
G5 | G. Approvals/portal | Expired/reused magic link | Expired page | P1 | Pass | /portal/ without a token redirects to a 'This link has expired' page with no access. Copy is misleading when there was never a link. | BUG-24 | Claude (QA) | 2026-09-27 | Pass
G6 | G. Approvals/portal | Comments own vs others | Others blocked | P1 | Blocked |  |  | Claude (QA) | 2026-09-27
G7 | G. Approvals/portal | Version diff | Shows diff | P2 | Blocked |  |  | Claude (QA) | 2026-09-27
G8 | G. Approvals/portal | Reminder email once | Once | P2 | Blocked |  |  | Claude (QA) | 2026-09-27
G9 | G. Approvals/portal | Portal pages scoped to client | Scoped | P1 | Blocked |  |  | Claude (QA) | 2026-09-27
H1 | H. CSV import | Editor imports 20-row CSV | Preview then import | P1 | Fail | 'Validate & Preview' returns Server Error (500) even for a clean 1-row CSV. Log: AttributeError: type object 'SocialAccount' has no attribute 'Platform' (apps/composer/views.py line 3434, csv_preview). | BUG-16 | Claude (QA) | 2026-09-27 | Fail
H2 | H. CSV import | Contributor import -> Pending review | Pending | P0 | Blocked | Blocked by H1. | BUG-16 | Claude (QA) | 2026-09-27
H3 | H. CSV import | Bad file -> row-level errors | Row errors | P1 | Fail | 500 instead of row errors. | BUG-16 | Claude (QA) | 2026-09-27 | Fail
I1 | I. Media library | Upload, folders, move, delete; persists after redeploy | Persists (S3) | P0 | Fail | Upload, reload and delete work. Storage is local disk (see PRE-4). Folders/move not tested. | BUG-03 | Claude (QA) | 2026-09-27 | Fail
I2 | I. Media library | Video thumbnail | Thumbnail | P2 | Fail | Existing MP4 shows a grey play icon, no thumbnail; the detail-panel player stays at 0:00 and never loads. | BUG-21 | Claude (QA) | 2026-09-27
I3 | I. Media library | Storage quota message | Clear | P2 | Not run |  |  | Claude (QA) | 2026-09-27
J1 | J. Beta features | Inbox shows comments | Shown | P2 | Blocked |  |  | Claude (QA) | 2026-09-27
J2 | J. Beta features | Inbox reply/notes/assign | Saved | P2 | Blocked |  |  | Claude (QA) | 2026-09-27
J3 | J. Beta features | Analytics numbers; no crash on empty | No crash | P2 | Pass | Empty state renders without error (no accounts). |  | Claude (QA) | 2026-09-27
J4 | J. Beta features | Bell unread count polls | Updates | P1 | Not run |  |  | Claude (QA) | 2026-09-27
J5 | J. Beta features | Failed publish notifies owner | In-app + email | P0 | Blocked | No SMTP, no accounts. | BUG-02 | Claude (QA) | 2026-09-27
K1 | K. Permissions | Viewer writes all 403 | 403 | P0 | Blocked | Needs role users (SMTP). |  | Claude (QA) | 2026-09-27
K2 | K. Permissions | Contributor cannot publish directly | Pending review | P0 | Blocked |  |  | Claude (QA) | 2026-09-27
K3 | K. Permissions | Editor cannot manage members/billing | Blocked | P0 | Blocked |  |  | Claude (QA) | 2026-09-27
K4 | K. Permissions | Client blocked from internal pages | Blocked | P0 | Blocked |  |  | Claude (QA) | 2026-09-27
K5 | K. Permissions | Removed member old tab | Redirect login | P0 | Blocked |  |  | Claude (QA) | 2026-09-27
L1 | L. Tenant isolation | Org B opens Org A URLs | 403/404 | P0 | Fail | All 15 Org A workspace pages returned 403 to an outsider account (good). BUT Org A's media file /media/media_library/2026/09/vasavi-atlantis-meta-9x16.mp4 downloads for the outsider AND for a logged-out browser. Any unpublished client asset is public to anyone who has or guesses the URL. | BUG-17 | Claude (QA) | 2026-09-27 | Fail
L2 | L. Tenant isolation | Org B writes to Org A by changing IDs | Refused | P0 | Pass | Media upload and compose save into Org A's workspace from Org B returned 403. |  | Claude (QA) | 2026-09-27
L3 | L. Tenant isolation | Org A magic link while logged in as Org B | Scoped | P0 | Blocked | No SMTP. |  | Claude (QA) | 2026-09-27
L4 | L. Tenant isolation | Org A API key on Org B | Refused | P0 | Not run |  |  | Claude (QA) | 2026-09-27
L5 | L. Tenant isolation | Search/notifications/exports scoped | Scoped | P0 | Not run |  |  | Claude (QA) | 2026-09-27
M1 | M. Security | XSS strings everywhere | Plain text | P0 | Partial | Escaped in idea title/body, composer caption and CSV preview table. Emails, portal, workspace/display names not tested. |  | Claude (QA) | 2026-09-27
M2 | M. Security | SSRF link preview | Refused | P0 | Not run |  |  | Claude (QA) | 2026-09-27
M3 | M. Security | Webhooks secret + rate limit | Rejected / 429 | P0 | Not run | WEBHOOK_SECRET not set (PRE-6). | BUG-04 | Claude (QA) | 2026-09-27
M4 | M. Security | No default superuser; admin throttled | Throttled | P0 | Fail | Django admin login is public at /admin/ and the pre-deploy command re-creates a superuser from env vars on every deploy (known hole). Brute force not attempted. | BUG-07 | Claude (QA) | 2026-09-27 | Partial
M5 | M. Security | HTTPS, cookie flags, no stack traces | Clean | P0 | Pass | HSTS, CSP, X-Frame-Options, nosniff, Referrer-Policy, COOP present; session cookie not readable by JS; 500s show a toast, no trace. Permissions-Policy header missing (minor). |  | Claude (QA) | 2026-09-27
M6 | M. Security | SVG with script / HTML as .png | Rejected | P0 | Pass | Both rejected server-side (UX issue in BUG-15). |  | Claude (QA) | 2026-09-27
M7 | M. Security | CSRF from another site | Rejected | P0 | Not run |  |  | Claude (QA) | 2026-09-27
N1 | N. Publisher | 20 posts over 2 h, >=99% on time | 99% | P0 | Blocked | No accounts; worker command wrong. | BUG-06 | Claude (QA) | 2026-09-27
N2 | N. Publisher | 5 posts same minute | All once | P0 | Blocked |  |  | Claude (QA) | 2026-09-27
N3 | N. Publisher | Worker restart | Exactly once | P0 | Blocked |  |  | Claude (QA) | 2026-09-27
N4 | N. Publisher | Worker down 15 min | Publish or marked missed | P1 | Blocked |  |  | Claude (QA) | 2026-09-27
N5 | N. Publisher | Temporary error retries | Backoff | P1 | Blocked |  |  | Claude (QA) | 2026-09-27
N6 | N. Publisher | Permanent error | Fails once | P0 | Blocked |  |  | Claude (QA) | 2026-09-27
N7 | N. Publisher | One platform fails | Others publish | P1 | Blocked |  |  | Claude (QA) | 2026-09-27
N8 | N. Publisher | First comment | Posted | P2 | Blocked |  |  | Claude (QA) | 2026-09-27
O1 | O. Ops | Deploy while users work | No loss | P1 | Not run |  |  | Claude (QA) | 2026-09-27
O2 | O. Ops | Restore DB backup | Row counts match | P0 | Not run | No evidence of a backup. |  | Claude (QA) | 2026-09-27
O3 | O. Ops | Media after 2 redeploys | Loads | P0 | Fail | Local disk, no volume: guaranteed loss on redeploy (by configuration). | BUG-03 | Claude (QA) | 2026-09-27 | Fail
O4 | O. Ops | /health/ with DB down | Non-200 | P2 | Not run |  |  | Claude (QA) | 2026-09-27
O5 | O. Ops | Sentry from web + worker | Both | P1 | Fail | Not configured. Also every Railway log line (even 404 warnings) is tagged severity 'error', which buries real errors. | BUG-04 | Claude (QA) | 2026-09-27 | Fail
O6 | O. Ops | All transactional emails | Arrive, branded | P1 | Blocked | No SMTP. | BUG-02 | Claude (QA) | 2026-09-27
P1 | P. Accessibility | Keyboard-only core flow | Visible focus | P1 | Partial | Login: all controls reachable, focus visible. App flow not completed (no accounts). |  | Claude (QA) | 2026-09-27
P2 | P. Accessibility | Modal focus trap + Esc | Trapped, returns | P1 | Fail | Create Idea modal: focus stays on the trigger, Tab moves to the page behind, no role='dialog'/aria-modal. Esc does close it. | BUG-18 | Claude (QA) | 2026-09-27
P3 | P. Accessibility | Screen reader | Announced | P2 | Not run |  |  | Claude (QA) | 2026-09-27
P4 | P. Accessibility | Contrast on primary buttons/body | No failures | P2 | Fail | White on olive 'Sign In' button 2.7:1; white on orange #F97316 buttons 2.8:1; orange links 2.7-2.8:1; 'SM BEAN · STUDIO' eyebrow 2.7:1; 'OR' divider 2.5:1. WCAG AA needs 4.5:1. | BUG-19 | Claude (QA) | 2026-09-27
P5 | P. Accessibility | Zoom 200% | No overlap | P2 | Not run |  |  | Claude (QA) | 2026-09-27
Q1 | Q. Mobile | Smoke on iPhone/Android | Works | P1 | Partial | Login and portal-expired pages fit at 375 px. App shell not tested on mobile. |  | Claude (QA) | 2026-09-27
Q2 | Q. Mobile | Calendar on phone | Usable | P1 | Not run |  |  | Claude (QA) | 2026-09-27
Q3 | Q. Mobile | Upload from camera roll | Works | P1 | Not run |  |  | Claude (QA) | 2026-09-27
Q4 | Q. Mobile | Chrome/Safari/Firefox/Edge | Same | P1 | Not run | Chrome only this round. |  | Claude (QA) | 2026-09-27
R1 | R. Public pages | Landing/pricing claims true | True | P1 | Fail | /pricing/ 404. Signup subtitle promises 'approvals across 10+ platforms' — only Bluesky, Mastodon and DEV.to are usable by beta users today. | BUG-22 | Claude (QA) | 2026-09-27 | Fail
R2 | R. Public pages | Terms/Privacy/Support links | Real pages | P0 | Fail | /terms/ /privacy/ /support/ 404. Signup 'Terms of Service' and 'Privacy Policy' link to brightbean.xyz — another product's legal pages. | BUG-08 | Claude (QA) | 2026-09-27 | Fail
R3 | R. Public pages | Brand sweep, no BrightBean | SM Bean only | P2 | Fail | Login/signup logo is 'brightbean-studio-logo.webp' (mascot badge reads 'STUDIO'); eyebrow 'SM BEAN · STUDIO'; legal links to brightbean.xyz. | BUG-23 | Claude (QA) | 2026-09-27 | Fail
R4 | R. Public pages | Branded 404/403 | Branded | P2 | Fail | 404 is a raw serif 'Not Found' page; 403 is a 135-byte plain response. No way back home. | BUG-24 | Claude (QA) | 2026-09-27 | Fail
R5 | R. Public pages | robots.txt, titles | Present | P2 | Fail | robots.txt 404; no meta robots; several pages titled just 'SM Bean' (Workspaces, Notifications, Social accounts, Ideas, Publish queue). | BUG-25 | Claude (QA) | 2026-09-27 | Fail
S1 | S. Performance | Main pages < 2 s | < 2 s | P2 | Pass | Server responses 0.3-0.65 s (empty workspace). Retest with 200 posts/files. |  | Claude (QA) | 2026-09-27
S2 | S. Performance | 50 MB video upload | Completes | P2 | Not run |  |  | Claude (QA) | 2026-09-27
S3 | S. Performance | Loading indicators, no double submit | Shown | P1 | Not run |  |  | Claude (QA) | 2026-09-27

## Bugs
Bug ID | Severity | Area | Title | Steps to reproduce | Expected | Actual | Evidence | Suggested fix | Status (retest 27 Sep) | Linked tests | Owner | Target date | Retest notes (27 Sep, 2 PM IST) | Eng retest 27 Sep (release code, Chromium) | Evidence | Live in production? | To close it
BUG-01 | P0 | Release | Production is still running pre-PR-#1 code | Check Railway deployments for sm-bean and sm-bean-worker | PR #1 deployed | Last deploy 24 Sep, commit 566b08c. Every PR #1 fix (terms, pricing, logout POST, robots) is missing | Railway deployments list; /terms/ 404 | Take a DB backup, merge PR #1, redeploy both services, re-run smoke | Open | PRE-1 |  |  | Release #3 (226ed66) FAILED on the web service at 08:07 UTC: gunicorn crashes on start with 'io.UnsupportedOperation: File or stream is not seekable' (error log pointed at a pipe). Web still runs 21052a5; worker runs 226ed66. See BUG-31/32. | Fixed in PR #4 | Release 226ed66 failed only because of BUG-31/32 (both fixed and verified). Backup step did run in prod: backups/db-20260927T080207Z.tar.gz written to the bucket. | Yes: web and worker both on dbe5301 (1 Oct 09:01 UTC) | Closed
BUG-02 | P0 | Email | No SMTP configured: no email can be sent | Railway > sm-bean > Variables | EMAIL_HOST etc. set | No email variables. Invites, password reset, magic links, approval requests, failure alerts all dead | Variable list | Add a transactional provider (Postmark/SES/Resend), set vars, verify SPF/DKIM/DMARC on the sending domain | In progress | PRE-3, SMK-4, SMK-5, SMK-9, A3, A7, C2, G3, J5, O6 |  |  | GMAIL_CLIENT_ID/SECRET, EMAIL_BACKEND_TYPE, DEFAULT_FROM_EMAIL added, but the web service never deployed the code that uses them. Not verifiable yet. | Code ready | Gmail API backend + /ops/email/ page render for superuser; client ID/secret set on web+worker. | Code live; Gmail not connected yet | Owner: connect Gmail at /ops/email/, send test email
BUG-03 | P0 | Storage | Media stored on container disk, not S3 | Upload an image; inspect URL | S3/R2 URL, persists across deploys | Served from /media/media_library/YYYY/MM/<file> on the web container; no volume, no S3 vars | Network tab; Railway config | Configure django-storages with S3/R2 (private bucket, signed URLs), migrate existing files | Open | PRE-4, SMK-6, I1, O3 |  |  | S3_* variables and STORAGE_BACKEND added, but a new upload at 08:25 UTC was still stored at /media/media_library/2026/09/qa-retest-s3.png (local disk). | Code ready | S3 credentials proven in prod: the pre-deploy backup wrote to bucket sm-bean-media. Uploads still local only because the web build never went live. | Yes: pre-deploy backup db-20261001T090041Z.tar.gz in bucket; legacy media 1 copied, 1 lost (vasavi-atlantis-meta-9x16.mp4 404 on old disk) | Re-upload that one video
BUG-04 | P1 | Ops | Sentry, SUPPORT_EMAIL, WEBHOOK_SECRET missing; all logs tagged 'error' | Railway variables and logs | Set; correct log levels | Not set; 404 warnings appear as severity error | Railway logs | Set vars; route INFO/WARNING to stdout at correct level (JSON logging) | Partly fixed | PRE-5, PRE-6, SMK-12, M3, O5 |  |  | SUPPORT_EMAIL and WEBHOOK_SECRET now set. SENTRY_DSN still missing (app's own check smbean.W005 warns on boot). | Partly fixed | Gunicorn + app logs are JSON on stdout with real levels (verified locally). SENTRY_DSN still unset. | Partly: gunicorn logs now level=info JSON; SENTRY_DSN still unset (W005 at boot) | Owner: set SENTRY_DSN
BUG-05 | P0 | Auth | Anyone can sign up with any email (invite-only not enforced) | Logged out, open /accounts/signup/, submit any email + password | 'Signup is invite only' page, no account | Account and workspace created immediately; no invite, no email verification | Created qa-test-noninvited@example.com during test (please delete) | Set SIGNUP_MODE=invite_only + SIGNUP_ALLOWLIST; enforce in allauth adapter for email and Google paths; require email verification | Open | PRE-7, SMK-3, A2 |  |  | SIGNUP_MODE is set but not live. Retest signup with qa-test-noninvited2@example.com created an account + workspace again. No SIGNUP_ALLOWLIST variable. ACCOUNT_EMAIL_VERIFICATION still 'none' (W009). | Pass | Signup page shows 'invite-only' screen, no form; stranger POST creates no account (DB count 0). Invite links admit only the invited address (unit test). | Yes: /accounts/signup/ shows 'invite-only' page | Closed
BUG-06 | P0 | Publisher | Worker runs the wrong command | Railway > sm-bean-worker > Start command | run_worker | python manage.py process_tasks | Service config | Set start command to run_worker after PR #1; restart after migrations | Fixed (config) | PRE-8, SMK-10, N1 |  |  | Worker start command is now 'python manage.py run_worker'. But the worker now errors every minute — see BUG-32. | Pass (config) | Worker start command is run_worker. Its current errors are BUG-32. | Yes: worker runs run_worker, 'recurring schedules verified' | Closed
BUG-07 | P0 | Security | Pre-deploy re-creates superuser and resets its password on every deploy | Railway > sm-bean > pre-deploy command | No superuser bootstrap in prod | DJANGO_SUPERUSER_EMAIL/PASSWORD set; shell snippet sets password every deploy; /admin/ publicly reachable | Service config | Remove the snippet and vars, rotate the admin password, restrict /admin/ (IP allowlist or 2FA) and throttle it | Partly fixed | PRE-9, M4 |  |  | Pre-deploy no longer creates/resets the superuser. DJANGO_SUPERUSER_EMAIL/PASSWORD are still stored on the service (delete + rotate). /admin/ still public (W010: set ADMIN_ALLOWED_IPS). | Partly fixed | Pre-deploy no longer touches the superuser. ADMIN_ALLOWED_IPS / ADMIN_URL available. | Partly: admin reachable from any IP (W010 at boot) | Owner: ADMIN_ALLOWED_IPS, delete DJANGO_SUPERUSER_*, rotate password
BUG-08 | P0 | Legal | Terms and Privacy missing; signup links to another company's legal pages | Open /terms/, /privacy/; check signup footer links | Own legal pages | 404; signup links to brightbean.xyz/terms-of-service and /privacy-policy | Page source of /accounts/signup/ | Publish real Terms/Privacy (DPDP + GDPR basics, Meta/Google data-use wording needed for app review) and relink | Open | PRE-11, R2 |  |  | /terms/ /privacy/ /support/ still 404. Legal links still go to brightbean.xyz — now also in the footer of every new marketing page. | Pass | /terms/ /privacy/ /support/ 200; privacy has DPDP + Google Limited Use + Meta terms; no brightbean.xyz anywhere. | Yes: /terms/ /privacy/ /support/ 200, own content, no brightbean.xyz | Legal review, then LEGAL_PAGES_REVIEWED=true
BUG-09 | P0 | QA setup | No test social accounts connected | Open Social accounts | Bluesky, Mastodon, DEV.to + Meta/YouTube tester accounts | 0 accounts | Connect page | Create and connect dedicated test accounts before the next round | Open | PRE-12, SMK-7, SMK-8, D1 |  |  | Still 0 connected accounts. | Owner action | — | No | Connect Bluesky, Mastodon, DEV.to test accounts
BUG-10 | P1 | Auth | Logout works over GET; logout is a link | Visit /accounts/logout/ in any tab or via an <img> on another site | Confirmation page / POST button | User is signed out silently | Reproduced in Chrome and in-app browser | ACCOUNT_LOGOUT_ON_GET=False; turn sidebar item into a POST form button | Open | A9, A10 |  |  | Sidebar 'Log out' is still a plain <a href=/accounts/logout/> with no form. | Pass | Sidebar logout is a POST form; GET /accounts/logout/ = 405 and session kept. | Yes: GET /accounts/logout/ returns 405 | Closed
BUG-11 | P1 | Onboarding | No onboarding checklist for new users | Sign up; land in app | 4-step checklist | Straight to Publish with a generic empty state | Screenshot 01 | Build the checklist card on first run (connect, post, idea, invite) with progress | Open | B1 |  |  | No checklist visible; same 'Welcome' empty state. | Pass | 'Get started — 0 of 4 complete' checklist on Publish. | Yes (dbe5301, 1 Oct). Behind login: needs QA retest signed in | Deploy PR #4
BUG-12 | P1 | Social | Sidebar promotes platforms that cannot be connected | Look at sidebar 'CONNECT CHANNELS' | Only ready platforms | 'LinkedIn (Company Page)' and 'TikTok' shown as first suggestions | Screenshot 01 | Drive the sidebar list from configured platforms; label others 'Coming soon' | Open | D7 |  |  | Sidebar still suggests LinkedIn (Company Page) and TikTok; connect page still says 'Not Configured' (4x). | Pass | Sidebar lists only Bluesky, Mastodon, DEV.to; connect page says 'Coming soon'. | Yes (dbe5301, 1 Oct). Behind login: needs QA retest signed in | Deploy PR #4
BUG-13 | P0 | Composer | Save Draft with no account silently discards the post | Compose > type caption > Save Draft (no channel selected) | Draft saved, or clear error | 204, redirect to Publish, no message, '0 drafts' | Network: POST compose/save/ 204 | Allow account-less drafts (drafts should not need a channel) or block with inline error; never 204 on a no-op | Open | E1, E14 |  |  | Save Draft still returns 204 and '0 drafts' (retest 08:24 UTC). | Pass | Save Draft with no channel: stays on composer at /compose/<id>/, 'Saved' shown, listed on Drafts page and in Publish > Drafts with 'No channel yet'. | Yes (dbe5301, 1 Oct). Behind login: needs QA retest signed in | Deploy PR #4
BUG-14 | P1 | Composer | Idea 'Create Post' makes an invisible ghost post and drops the title | Idea > Create Post | Draft visible in Drafts, title kept | Post record exists only by URL; Drafts shows 0; title lost | Post 5265c8a5… (deleted after test) | Include account-less posts in Drafts; map idea title into caption or post title | Not retested | E4, E16 |  |  | Needs the E1 fix first. | Pass | Channel-less posts visible in Drafts (browser); idea title kept/seeds caption (unit tests). | Yes (dbe5301, 1 Oct). Behind login: needs QA retest signed in | Deploy PR #4
BUG-15 | P1 | Media | Rejected uploads fail silently | Upload a text file renamed .jpg | Inline error naming the reason | HTTP 200 empty body, page reloads, file gone | Network | Return 400 with per-file errors and show them in the uploader | Open | E8 |  |  | Fake .jpg upload still returns 200 with an empty body. | Pass | fake.jpg → HTTP 400, uploader shows '1 file was not uploaded: Unsupported or unrecognised file type'. | Yes (dbe5301, 1 Oct). Behind login: needs QA retest signed in | Deploy PR #4
BUG-16 | P1 | CSV import | CSV preview crashes (500) on every file | Import CSV > Upload > Validate & Preview | Preview with row errors | Server Error (500): AttributeError SocialAccount.Platform (views.py:3434) | Railway logs 06:21 and 06:22 UTC | Use the correct platform enum (e.g. SocialAccount.platform choices / Platform model); add a unit test for csv_preview | Open | H1, H2, H3 |  |  | CSV preview still 500 — same AttributeError SocialAccount.Platform at 08:25 UTC. | Pass | CSV Validate & Preview → HTTP 200 with row errors: Invalid date, Unknown platform, Caption is empty. | Yes (dbe5301, 1 Oct). Behind login: needs QA retest signed in | Deploy PR #4
BUG-17 | P0 | Security | Media files are public to anyone with the URL (cross-tenant) | Log out (or log in as Org B), open /media/media_library/2026/09/<file> | 403 / signed URL | File downloads (200/206) | Tested logged-out and as outsider | Private bucket + short-lived signed URLs, or an auth-checked media view; random (UUID) filenames | Open | L1 |  |  | Org A video still downloads (200) for a logged-out browser. | Pass | Upload 'client-launch-teaser.png' stored as media_library/2026/09/73c27ca7…dd721.png; in prod files move to the private bucket with 1-hour signed URLs. | Yes (dbe5301, 1 Oct). Behind login: needs QA retest signed in | Deploy PR #4
BUG-18 | P1 | Accessibility | Modals do not manage focus | Create Idea > press Tab | Focus inside dialog, trapped | Focus stays on trigger; Tab reaches page behind; no dialog role | Keyboard test | Use a dialog primitive (native <dialog> or focus-trap), role=dialog, aria-modal, return focus | Not retested | P2 |  |  | No UI change seen. | Pass | Create Idea: role=dialog aria-modal, focus starts in title, stays inside after 6×Tab, Esc closes. | Yes (dbe5301, 1 Oct). Behind login: needs QA retest signed in | Deploy PR #4
BUG-19 | P2 | Design | Brand colours fail contrast | Measure primary buttons/links | ≥4.5:1 | 2.5-2.8:1 | Contrast script | Darken brand orange to ~#C2410C and olive to ~#5F6B1F for text/buttons; keep bright tints for fills | Not retested | P4 |  |  | Same colours visible. | Pass | Primary 'New' button background rgb(194,65,12) = #C2410C (5.2:1 with white). | Yes (dbe5301, 1 Oct). Behind login: needs QA retest signed in | Deploy PR #4
BUG-20 | P2 | Publish | Empty state hijacks Publish tabs and Calendar toggle | No channel connected; click Drafts, then Calendar | Show drafts; switch view | Every tab shows 'Welcome'; first Calendar click ignored | Screenshot 03 | Show empty state as a banner, keep tabs functional | Open | F1, F8 |  |  | Publish tabs still show the Welcome state. | Pass | One 'No channels connected yet' banner; Queue/Drafts/Approvals/Sent keep their own content; Calendar toggle works on first click. | Yes (dbe5301, 1 Oct). Behind login: needs QA retest signed in | Deploy PR #4
BUG-21 | P2 | Media | Video has no thumbnail and preview player never loads | Media > open MP4 | Thumbnail + playable | Grey icon; player stuck at 0:00 | Screenshot 05 | Generate poster frame on upload; serve with Range support | Not retested | I2 |  |  |  | Unit-tested | Detail player uses Range-capable stream + poster; uploads queue thumbnail job (tests). Not browser-tested: no video fixture. | Yes (dbe5301, 1 Oct). Behind login: needs QA retest signed in | Deploy PR #4; QA retest with an MP4
BUG-22 | P1 | Content | Signup copy over-promises platforms; pricing page missing | Open signup, /pricing/ | Accurate claims | '10+ platforms'; /pricing/ 404 | Screenshot 02 | Say 'Bluesky, Mastodon and DEV.to today; Meta and YouTube coming soon' | Open (worse) | R1 |  |  | /pricing/ still 404. New marketing home page claims '11 networks' (6 times); only 3 are usable by beta users. | Pass | Home/platforms/pricing list live = Bluesky, Mastodon, DEV.to, rest 'Coming soon'; no '10+'/'11 networks'; /pricing/ 200. | Yes (dbe5301, 1 Oct). Behind login: needs QA retest signed in | Deploy PR #4
BUG-23 | P2 | Brand | BrightBean leftovers | Login/signup | SM Bean brand only | BrightBean Studio mascot logo ('STUDIO' badge), 'SM BEAN · STUDIO' | Screenshot 02 | Replace logo and eyebrow; grep templates/static for 'brightbean' | Open (worse) | R3 |  |  | BrightBean Studio logo now on every marketing page; footer links to github.com/brightbeanxyz/brightbean-studio and a 'Self-host it' page. | Pass | No BrightBean logo, 'Studio' tag or brightbean.xyz on login, signup, marketing pages. | Yes on login, signup, marketing; marketing 'Source code' links still went to upstream repo: fixed in PR #5 | Merge PR #5
BUG-24 | P2 | Errors | Unbranded 404/403 and misleading portal 'expired' page | Open a bad URL; open /portal/ with no link | Branded pages with a way home | Raw 'Not Found'; 403 plain text; portal says link 'expired' though none was used | Screenshot 04 | Add 404.html/403.html/500.html in the app shell; separate 'invalid link' vs 'expired link' copy | Open | G5, R4 |  |  | Raw 404 unchanged. | Pass | Branded 404 with link home; /portal/ → 'Sign in with your approval link'; bad token → 'This link isn't valid'. | Yes: branded 404; invalid portal link shows 'This link isn't valid' | Closed
BUG-25 | P2 | SEO/meta | No robots.txt, missing page titles | Open /robots.txt; check <title> | robots.txt disallows app; unique titles | 404; 6 pages titled 'SM Bean' | Crawl table | Add robots.txt and noindex on app pages; set titles per page with one separator style | Open | R5 |  |  | robots.txt still 404; Workspaces, Notifications, Social accounts still titled just 'SM Bean'. | Pass | robots.txt + sitemap 200; titles 'Workspaces · SM Bean', 'Notifications · SM Bean'. | Yes: robots.txt + sitemap, page titles on every public page | Closed
BUG-26 | P3 | QA plan | Plan links point at internal endpoints | Open /workspace/{ws}/tags/ and /ideas/board/ | Pages | Raw JSON '[]' and an unstyled HTMX fragment | Screenshots | Update plan: Ideas is /workspace/{ws}/create/; tags are managed inside composer | Open | E11 |  |  | /tags/ still returns JSON. | Plan update | /tags/ is an internal JSON endpoint by design; Ideas live at /workspace/{ws}/create/. | n/a | QA: update test plan
BUG-27 | P3 | Copy | Timezone shown as 'Calcutta'; media times in UTC | Publish filter; Media detail | 'Kolkata'; workspace time | 'Calcutta (workspace)'; upload time 6:19 AM (UTC) for an 11:49 AM IST upload | Screenshot 05 | Use current IANA names in labels; render all times in workspace tz | Open | C6 |  |  | 'Calcutta (workspace)' still shown; media upload time shown as 8:25 AM (UTC) for a 1:55 PM IST upload. | Pass | Timezone filter shows 'Kolkata (workspace)'; data migration rewrites stored Asia/Calcutta; media times use workspace tz. | Yes (dbe5301, 1 Oct). Behind login: needs QA retest signed in | Deploy PR #4
BUG-28 | P2 | Layout | Media library layout defects | Open Media library | Clean layout | 'FOLDERS' heading clipped to 'OLDERS'; Upload button clipped; new upload renders as a full-width giant card until reload; detail drawer overflows off-screen (close X and Delete cut) | Screenshots 05-06 | Fix container padding/overflow; constrain new card to grid; drawer max-width: 100vw | Partly fixed |  |  |  | Detail drawer now fits the screen. 'FOLDERS' heading still clipped to 'OLDERS'. | Pass | 'Folders' heading at x=291 inside content (x=250), not clipped; Upload visible; drawer fits. | Yes (dbe5301, 1 Oct). Behind login: needs QA retest signed in | Deploy PR #4
BUG-29 | P3 | Navigation | Wrong active nav item on composer; stray scroll arrows beside Publish tabs | Open composer; look at Publish tabs | Correct highlight; no widget | 'Create Idea' highlighted on New Post; tiny up/down scroll control beside 'Sent' | Screenshot 01/03 | Fix active-route matching; hide tab-row overflow scrollbar | Open |  |  |  | Composer still highlights 'Create Idea'. | Pass | On New Post no nav item is marked current (Create Idea not highlighted); tab-row scrollbar hidden. | Yes (dbe5301, 1 Oct). Behind login: needs QA retest signed in | Deploy PR #4
BUG-30 | P2 | Design | Inconsistent visual language | Compare login, reset, app, analytics, portal | One system | Olive primary on login, orange on reset/app; serif headings on Analytics/portal vs sans elsewhere; three different button styles for primary actions | Screenshots | Define tokens (one primary, one type family, 3 button variants) and apply | Not retested |  |  |  |  | Partly fixed | One primary colour everywhere (olive removed). Serif headings on Analytics/portal + real wordmark still need design. | Yes (dbe5301, 1 Oct). Behind login: needs QA retest signed in | Design pass
BUG-31 | P0 | Release | Web deploy of the QA-fix release crashes on start | Railway > sm-bean > deployment fe991b60 (commit 226ed66) | Healthy deploy | gunicorn: 'io.UnsupportedOperation: File or stream is not seekable' at glogging.setup (open(cfg.errorlog,'a+')). Healthcheck failed; Railway kept the old 21052a5 build live. | Railway deploy logs 08:02 UTC | Set gunicorn --error-logfile - and --access-logfile - (dash = stderr/stdout), not /dev/stdout; redeploy | Open |  |  |  | New bug found in retest, 27 Sep | Fixed in PR #4 | Reproduced locally (old flags → 'File or stream is not seekable'); new gunicorn.conf.py boots, /health/ 200, JSON logs on stdout. | Yes: gunicorn booted, /health/ 200 with database+cache checks | Closed
BUG-32 | P0 | Publisher | Worker and database are on different versions: worker errors every minute | Railway > sm-bean-worker logs since 08:00 UTC | Worker tasks succeed | Worker runs new code (226ed66) but the new migrations never ran (web deploy failed). 'retry_failed_deliveries' fails every minute: column notifications_notification.shown_in_app does not exist. Thumbnail/metadata tasks also failing. | Railway worker logs (23 failures in 25 min) | Roll the worker back to 21052a5 now, or fix BUG-31 so web deploys and migrate runs; make web and worker deploy together | Open |  |  |  | New bug found in retest, 27 Sep | Fixed in PR #4 | Pre-deploy ran only the backup (Railway runs it without a shell). New 'manage.py release' = backup → migrate → media import; rehearsed from prod's schema: all migrations applied, shown_in_app exists. Pre-deploy already switched. | Yes: release ran backup then 8 migrations then media import; worker errors stopped | Closed
BUG-33 | P1 | Brand/Content | New marketing site ships BrightBean links, over-claims and a self-host page | Open /, /features/, /platforms/, /get-started/ | SM Bean brand, honest claims | BrightBean Studio logo, brightbean.xyz legal links, GitHub link to brightbeanxyz/brightbean-studio, 'Self-host it' page, '11 networks' | Page source | Rebrand marketing templates, remove self-host/open-source links for the hosted beta, list only the 3 live platforms | Open |  |  |  | New bug found in retest, 27 Sep | Pass | Marketing logo = SM Bean monogram; footer legal → /terms/ /privacy/ /support/; only 3 live networks claimed; CTAs 'Request early access'. Source-code link kept (AGPL-3.0 §13 requires offering source to users). | Yes except 'Source code' links → upstream repo; fixed in PR #5 | Merge PR #5; product decision on self-host page
BUG-34 | P0 | Release | Folder-name migration could abort the deploy or rename another tenant's folder | Review of media_library/0004 against 21052a5 data | Migration applies to any real data | IntegrityError 'could not create unique index' on duplicate org-wide subfolders or an existing 'X (2)'; cross-tenant renames | Reproduced on Postgres rewound to 0003 | Key includes organisation; de-duplicate every scope with a free suffix | Fixed – retest after deploy | — | Eng |  | Found in pre-deploy migration review (1 Oct) | Fixed in PR #4 | Old migration aborts in test; new one passes on every seeded shape | Yes: media_library.0004 applied OK on production data | Closed
BUG-35 | P1 | Publisher | Two workers during a deploy clone the same recurrence dates | Run the recurrence cycle in two workers at once | Each date cloned once | Duplicate scheduled posts (double publish once accounts exist) | Two-thread race test: 24 clones for 12 dates | Re-read the ledger under a row lock per occurrence | Fixed – retest after deploy | — | Eng |  | Found in pre-deploy migration review (1 Oct) | Fixed in PR #4 | Race test fails without the lock 3/3, passes with it 3/3 | Yes: worker live; first cycle 'Generated 0 recurring posts' (no surprise clones) | Closed

## Design & UX
# | Area | What we saw | Why it matters | Recommendation | Priority
1 | Brand colour | Two competing primaries: olive green (#93A240) on login/signup, orange (#F97316) everywhere else, including the password-reset page. | Feels like two products; weak recognition. | Pick one primary (keep orange, it owns the app). Use a darker text-safe shade (#C2410C) for text/buttons and the bright orange only for fills and highlights. | High
2 | Contrast | Primary buttons and links sit at 2.5-2.8:1. | Fails WCAG AA; hard to read on phones outdoors — exactly where clients approve posts. | Darken button backgrounds or switch button text to near-black on light orange. Target ≥4.5:1 for text. | High
3 | Logo & identity | Login uses the BrightBean Studio mascot (reads 'STUDIO'); eyebrow 'SM BEAN · STUDIO'. App sidebar shows a plain orange 'M' tile. | Agencies will notice it is a rebadged product; trust drops. | Commission a simple SM Bean wordmark + bean icon; use it on login, sidebar, favicon, emails and portal. | High
4 | Typography | System UI font in the app; serif display font on Analytics and the portal 'expired' card; raw Times-style 404. | Inconsistent tone. | One family (e.g. Inter or Geist) with a 5-step type scale; optional single display face for H1 only. | Medium
5 | First-run experience | New user lands on 'Publish' with a generic 'Welcome' illustration; tabs and Calendar are effectively locked; no checklist. | Day-one agency cannot tell what to do first; high drop-off risk. | Guided checklist card (Connect → Create post → Invite client → Schedule), progress bar, and a sample 'demo' post so the calendar is never empty. | High
6 | Empty & error states | Silent failures (draft save, rejected upload), raw 404/403, 500 as a tiny toast. | Users lose work without knowing; support load. | Every write returns a visible result: success toast, inline field error, or a full-page branded error with a next step. | High
7 | Navigation | Sidebar mixes actions ('New', 'Create Idea') with places; 'Connect channels' suggests unavailable platforms; wrong active item on composer. | Orientation cost. | Group as Plan (Calendar, Ideas) · Engage (Inbox) · Measure (Analytics) · Settings. Move 'Connect channels' into a dismissible setup card. | Medium
8 | Composer | Clean two-pane layout with preview (good). But no account picker visible when none connected, only grey 'No accounts connected'. | Primary task blocked with no guidance. | Show an account picker row always; when empty, a clear 'Connect your first channel' button inline. Keep Save Draft always available. | High
9 | Calendar | Past days rendered in heavy grey, today in orange; legend is clear. | Past-day grey is heavy and lowers legibility of past posts. | Lighter past-day tint; show post chips with platform icons and status colour; sticky week header. | Low
10 | Media library | Clipped header/upload button, giant card after upload, drawer overflowing viewport, no video thumbnails. | Looks unfinished. | Fix grid & drawer sizing, generate thumbnails, add upload progress list. | Medium
11 | Client portal | Clean, calm card. Copy says 'expired' for any invalid link. | Clients may think they missed a deadline. | Split 'invalid' vs 'expired'; add agency logo and a 'Request a new link' button that notifies the team. | Medium
12 | Accessibility | Visible focus on login (good); modals don't trap focus; no dialog roles. | Keyboard and screen-reader users get lost. | Adopt one accessible dialog component; run axe in CI. | Medium
13 | Microcopy | 'Not Configured' (developer wording); 'Calcutta'; '10+ platforms'. | Confusing / over-promising. | 'Coming soon', 'Kolkata', and an honest platform list. | Low
Proposed colour tokens
| primary-600 (buttons, links) | #C2410C | White text 5.2:1
| primary-500 (fills, highlights) | #F97316 | Use behind dark text only
| primary-50 (tints) | #FFF7ED | Backgrounds, selected rows
| ink-900 (body text) | #1C1917 | 17:1 on white
| ink-500 (secondary text) | #57534E | 7.3:1 on #FAFAF9
| success | #15803D | Published
| danger | #B91C1C | Failed / delete

## Exit Criteria
Exit criterion | Met? | Evidence
All pre-conditions ticked | No | 10 of 12 failed — see PRE-1…PRE-12
P0 smoke passed twice on two deploys | No | SMK-3, SMK-6 failed; 7 steps blocked
Zero open P0 and P1 bugs | No | See Summary
Sections K, L, M all passed | No | L1 and M4 failed; K blocked
Publish success ≥99% (N1), zero duplicates | No | Blocked
Worker restart test N3 passed 3× | No | Blocked
DB restore O2 proven | No | Not run
Transactional emails arrive, not spam | No | No SMTP
P2 bugs have owner and date | No | Owner/Target columns empty on Bugs tab
Beta testers told which platforms work | No | Signup still says 10+ platforms