## Summary
SM Bean — Closed-Beta QA Round 1: Results
Run 27 Sep 2026 on production (sm-bean-production-eb50.up.railway.app) · Chrome desktop + in-app browser mobile emulation · Tester: Claude (acting as QA agency) for Hemant
RECOMMENDATION
Result by status |  |  |  | Open bugs by severity
Status | Tests | % of total |  | Severity | Open bugs
Pass |  |  |  | P0
Fail |  |  |  | P1
Partial |  |  |  | P2
Blocked |  |  |  | P3
Not run |  |  |  | Total
Total
Failures by suite
Suite | Tests | Pass | Fail | Partial | Blocked / Not run
Pre-conditions
Smoke
A. Sign-in
B. Onboarding
C. Org/workspace
D. Social accounts
E. Composer
F. Calendar
G. Approvals/portal
H. CSV import
I. Media library
J. Beta features
K. Permissions
L. Tenant isolation
M. Security
N. Publisher
O. Ops
P. Accessibility
Q. Mobile
R. Public pages
S. Performance
Notes
• Why so many 'Blocked': the plan's pre-conditions were not met (no SMTP, no S3, no test social accounts, PR #1 not deployed). Every email, publishing and role test depends on them.
• Test data created and removed: 1 idea, 1 image, 1 ghost post (all deleted). Rejected uploads left nothing behind.
• Test data created and NOT removable by QA: user account qa-test-noninvited@example.com and its 'My Workspace' (created by the A2 signup test). Please delete it from /admin/.
• Nothing was published to any social platform and no one was invited or emailed.
• Edit the Status column on 'Test Results' and the Status column on 'Bugs' during retest — every number on this page recalculates.

## Test Results
Test ID | Suite | Test | Expected | Priority | Status | Actual result / notes | Bug | Tester | Date | Retest status
PRE-1 | Pre-conditions | Backup taken, PR #1 merged and deployed to web + worker | Latest code live | P0 | Fail | Last deploy on both services is 24 Sep (commit 566b08c 'fix(auth): CSRF_TRUSTED_ORIGINS'). PR #1 fixes are not live: /terms/, /pricing/, /robots.txt 404; logout still a GET link. | BUG-01 | Claude (QA) | 2026-09-27
PRE-2 | Pre-conditions | /health/ returns 200 | 200 | P0 | Pass | 200 {"status":"ok"} in ~0.3 s. |  | Claude (QA) | 2026-09-27
PRE-3 | Pre-conditions | SMTP settings set | Email works | P0 | Fail | No EMAIL_*/SMTP variables on the web service. Invites, resets, magic links and failure alerts cannot be sent. | BUG-02 | Claude (QA) | 2026-09-27
PRE-4 | Pre-conditions | S3 media storage set | Media on S3 | P0 | Fail | No AWS/S3 variables and no Railway volume. Media is written to the container disk and served from /media/…; it will be lost on the next redeploy. | BUG-03 | Claude (QA) | 2026-09-27
PRE-5 | Pre-conditions | Sentry DSN set | Errors captured | P1 | Fail | No SENTRY_DSN on web or worker. | BUG-04 | Claude (QA) | 2026-09-27
PRE-6 | Pre-conditions | SUPPORT_EMAIL and WEBHOOK_SECRET set | Set | P1 | Fail | Neither variable exists. | BUG-04 | Claude (QA) | 2026-09-27
PRE-7 | Pre-conditions | SIGNUP_ALLOWLIST holds testers; SIGNUP_MODE=invite_only | Invite-only | P0 | Fail | Neither variable exists. Open signup confirmed in A2. | BUG-05 | Claude (QA) | 2026-09-27
PRE-8 | Pre-conditions | Worker start command is run_worker, restarted after migrations | run_worker | P0 | Fail | Worker start command is 'python manage.py process_tasks'. | BUG-06 | Claude (QA) | 2026-09-27
PRE-9 | Pre-conditions | DJANGO_SUPERUSER_* deleted; pre-deploy no longer resets admin | Removed | P0 | Fail | Both variables still set; pre-deploy command re-creates the superuser and resets its password on every deploy. | BUG-07 | Claude (QA) | 2026-09-27
PRE-10 | Pre-conditions | Google sign-in client ID/secret + callback registered | Google works | P0 | Pass | GOOGLE_AUTH_CLIENT_ID/SECRET present; owner signed in. One 'Unauthorized: /accounts/google/login/callback/' seen in logs at 06:14 UTC — retest. |  | Claude (QA) | 2026-09-27
PRE-11 | Pre-conditions | Terms and Privacy pages live with real text | Live | P0 | Fail | /terms/ and /privacy/ return an unbranded 404. | BUG-08 | Claude (QA) | 2026-09-27
PRE-12 | Pre-conditions | Test social accounts ready | Connected | P0 | Fail | Workspace has 0 connected accounts. All publishing tests blocked. | BUG-09 | Claude (QA) | 2026-09-27
SMK-1 | Smoke | /health/ returns 200 | 200 | P0 | Pass | OK. |  | Claude (QA) | 2026-09-27
SMK-2 | Smoke | Google sign-in, allowlisted tester | Lands in app | P0 | Pass | Owner lands on Publish page. See PRE-10 note. |  | Claude (QA) | 2026-09-27
SMK-3 | Smoke | Non-allowlisted account is refused | Invite-only page, no account | P0 | Fail | Email signup with qa-test-noninvited@example.com created an account and workspace instantly, no invite, no email verification. | BUG-05 | Claude (QA) | 2026-09-27
SMK-4 | Smoke | Invite email arrives within 2 min | Arrives | P0 | Blocked | No SMTP configured (PRE-3). | BUG-02 | Claude (QA) | 2026-09-27
SMK-5 | Smoke | Password reset email works | Arrives | P0 | Blocked | No SMTP configured. | BUG-02 | Claude (QA) | 2026-09-27
SMK-6 | Smoke | Upload image, reload, still there (S3) | Persists on S3 | P0 | Fail | Image persisted after page reload, but it is stored on local container disk (/media/…), not S3. Will not survive a redeploy. | BUG-03 | Claude (QA) | 2026-09-27
SMK-7 | Smoke | Publish now to each ready platform | Published | P0 | Blocked | No connected test accounts. | BUG-09 | Claude (QA) | 2026-09-27
SMK-8 | Smoke | Scheduled post publishes within 1 min | On time | P0 | Blocked | No connected test accounts. | BUG-09 | Claude (QA) | 2026-09-27
SMK-9 | Smoke | Client magic-link approval | Approved | P0 | Blocked | No SMTP, no accounts. | BUG-02 | Claude (QA) | 2026-09-27
SMK-10 | Smoke | Worker restart during due post: exactly once | Once | P0 | Blocked | No accounts; worker on wrong command. | BUG-06 | Claude (QA) | 2026-09-27
SMK-11 | Smoke | 11 wrong passwords in 1 min -> 429 | 429 on 11th | P1 | Pass | Attempts 1-10 returned the error page, 11 and 12 returned 429 'Too many requests'. |  | Claude (QA) | 2026-09-27
SMK-12 | Smoke | Sentry shows test error | Visible | P1 | Blocked | Sentry not configured. | BUG-04 | Claude (QA) | 2026-09-27
A1 | A. Sign-in | New allowlisted user, Google | Onboarding | P0 | Blocked | Needs an allowlist (PRE-7) and a fresh Google test account. |  | Claude (QA) | 2026-09-27
A2 | A. Sign-in | Non-allowlisted, not invited user signs up | Invite-only page, no account | P0 | Fail | Email signup open to anyone; account + 'My Workspace' created at once. | BUG-05 | Claude (QA) | 2026-09-27
A3 | A. Sign-in | Invite link, then Google | Joins with role | P0 | Blocked | No SMTP. | BUG-02 | Claude (QA) | 2026-09-27
A4 | A. Sign-in | Existing user signs in with Google again | Same account | P0 | Pass | Owner account re-used (single member in org). Retest after callback 401 in logs. |  | Claude (QA) | 2026-09-27
A5 | A. Sign-in | Email user later uses Google, same email | Same account | P1 | Not run | Needs a second tester Google account. |  | Claude (QA) | 2026-09-27
A6 | A. Sign-in | Wrong then right password | Error, then success | P0 | Partial | Wrong password shows error. Right password not entered by QA (policy). |  | Claude (QA) | 2026-09-27
A7 | A. Sign-in | Password reset end to end | Works once | P0 | Blocked | No SMTP. | BUG-02 | Claude (QA) | 2026-09-27
A8 | A. Sign-in | 11 wrong passwords in 60 s | 429 | P1 | Pass | 429 from attempt 11. |  | Claude (QA) | 2026-09-27
A9 | A. Sign-in | Log out is a POST button | POST | P1 | Fail | Sidebar 'Log out' is a plain link to /accounts/logout/ (GET). | BUG-10 | Claude (QA) | 2026-09-27
A10 | A. Sign-in | GET /accounts/logout/ does not log out | Stays signed in | P2 | Fail | Visiting the URL signed the owner out immediately (reproduced twice, two browsers). | BUG-10 | Claude (QA) | 2026-09-27
A11 | A. Sign-in | Cancel on Google consent | Clear message | P2 | Not run |  |  | Claude (QA) | 2026-09-27
B1 | B. Onboarding | First login shows 4-item checklist | Checklist | P1 | Fail | No checklist on the owner dashboard; new signup lands straight on Publish with a 'Welcome — connect a channel' empty state. | BUG-11 | Claude (QA) | 2026-09-27
B2 | B. Onboarding | Items tick as completed | Ticks | P1 | Blocked | Depends on B1. |  | Claude (QA) | 2026-09-27
B3 | B. Onboarding | Dismiss persists | Hidden | P2 | Blocked | Depends on B1. |  | Claude (QA) | 2026-09-27
C1 | C. Org/workspace | Create second workspace, data separate | Separate | P0 | Not run | Not approved to create workspaces in production. |  | Claude (QA) | 2026-09-27
C2 | C. Org/workspace | Invite one user per role | Right role | P0 | Blocked | No SMTP. | BUG-02 | Claude (QA) | 2026-09-27
C3 | C. Org/workspace | Change role, remove member | Immediate | P1 | Blocked | Only one member. |  | Claude (QA) | 2026-09-27
C4 | C. Org/workspace | Client cannot open /members/ | Blocked | P1 | Blocked | No client user. |  | Claude (QA) | 2026-09-27
C5 | C. Org/workspace | Resend/revoke invite | Revoked link dead | P2 | Blocked | No SMTP. |  | Claude (QA) | 2026-09-27
C6 | C. Org/workspace | Timezone + approval mode saved and obeyed | Obeyed | P1 | Partial | Approvals page shows the 4 modes clearly. Save/behaviour not tested (no accounts). Timezone label says 'Calcutta' — use 'Kolkata'. | BUG-27 | Claude (QA) | 2026-09-27
D1 | D. Social accounts | Connect each ready platform | Connected | P0 | Blocked | No test accounts provided. | BUG-09 | Claude (QA) | 2026-09-27
D2 | D. Social accounts | Connect same account twice | No duplicate | P2 | Blocked |  |  | Claude (QA) | 2026-09-27
D3 | D. Social accounts | Disconnect account with scheduled posts | Posts to Draft + notice | P0 | Blocked |  |  | Claude (QA) | 2026-09-27
D4 | D. Social accounts | Remove only on disconnected | Confirmed | P1 | Blocked |  |  | Claude (QA) | 2026-09-27
D5 | D. Social accounts | Platform-side revoke | Fails once, needs reconnect | P0 | Blocked |  |  | Claude (QA) | 2026-09-27
D6 | D. Social accounts | Reconnect | Connected | P1 | Blocked |  |  | Claude (QA) | 2026-09-27
D7 | D. Social accounts | LinkedIn/TikTok/Pinterest hidden or labelled | Clear state | P1 | Fail | Connect page greys them out as 'Not Configured' (OK), but the sidebar 'CONNECT CHANNELS' block promotes 'LinkedIn (Company Page)' and 'TikTok' as the first things to connect. | BUG-12 | Claude (QA) | 2026-09-27
E1 | E. Composer | Save draft with text only | Appears in Drafts | P0 | Fail | With no account selected, Save Draft POST returns 204, redirects to Publish, shows no message, and nothing is saved. Drafts shows '0 drafts'. User text is lost silently. | BUG-13 | Claude (QA) | 2026-09-27
E2 | E. Composer | Schedule to 2 accounts | On time | P0 | Blocked | No accounts. |  | Claude (QA) | 2026-09-27
E3 | E. Composer | Publish now | Live < 1 min | P0 | Blocked | No accounts. |  | Claude (QA) | 2026-09-27
E4 | E. Composer | Zero accounts selected | Rejected with message + link; no ghost post | P0 | Fail | No message (see E1). 'Create Post' from an Idea creates a post record that never appears in Drafts/Queue (ghost post, reachable only by URL). | BUG-14 | Claude (QA) | 2026-09-27
E5 | E. Composer | Past time rejected | Message | P1 | Blocked |  |  | Claude (QA) | 2026-09-27
E6 | E. Composer | Character limit warning | Warns | P1 | Blocked | Preview needs a platform. |  | Claude (QA) | 2026-09-27
E7 | E. Composer | Upload JPG/PNG/MP4, remove one | Progress; removed not attached | P0 | Partial | PNG upload via media library works and persists. Composer attach/remove not tested (cannot save a post). |  | Claude (QA) | 2026-09-27
E8 | E. Composer | Oversized file and fake .jpg | Rejected with message | P1 | Fail | Fake .jpg, SVG-with-script and HTML-renamed-.png were all rejected (good) but the server answers 200 with an empty body and the page reloads: the user never learns why the file vanished. | BUG-15 | Claude (QA) | 2026-09-27
E9 | E. Composer | Unsplash import with attribution | Attached | P2 | Not run |  |  | Claude (QA) | 2026-09-27
E10 | E. Composer | Save as template / use template | Pre-filled | P2 | Not run |  |  | Claude (QA) | 2026-09-27
E11 | E. Composer | Tags and categories filter | Filters | P2 | Not run | Plan link /tags/ returns raw JSON '[]' in the browser — no tag management page at that URL. | BUG-26 | Claude (QA) | 2026-09-27
E12 | E. Composer | Edit scheduled post | Publishes once | P0 | Blocked |  |  | Claude (QA) | 2026-09-27
E13 | E. Composer | Clone and delete | Independent | P1 | Partial | Delete works with a clear confirm modal. Clone not tested. |  | Claude (QA) | 2026-09-27
E14 | E. Composer | Form error keeps text | Kept | P1 | Fail | Covered by E1: text discarded with no error. | BUG-13 | Claude (QA) | 2026-09-27
E15 | E. Composer | Autosave recovers text | Recovered | P2 | Partial | After 4 s of idle the footer still read 'Not saved yet'. Retest with a longer wait and a connected account. |  | Claude (QA) | 2026-09-27
E16 | E. Composer | Ideas board create/move/convert | Linked | P2 | Partial | Create, drag to 'To Do' and persistence work; XSS escaped. 'Create Post' drops the idea title (only the body is copied) and the post is invisible (E4). | BUG-14 | Claude (QA) | 2026-09-27
F1 | F. Calendar | Month/week/list in workspace tz | Correct | P0 | Partial | Month grid renders (workspace + org calendar). First click on 'Calendar' toggle did nothing; second worked. Could not verify placement (no posts). | BUG-20 | Claude (QA) | 2026-09-27
F2 | F. Calendar | Drag to reschedule | New time | P0 | Blocked |  |  | Claude (QA) | 2026-09-27
F3 | F. Calendar | Concurrent drag -> 409 | 409 message | P1 | Blocked |  |  | Claude (QA) | 2026-09-27
F4 | F. Calendar | Recurring post | Each once | P1 | Blocked |  |  | Claude (QA) | 2026-09-27
F5 | F. Calendar | Calendar events CRUD | Valid | P2 | Not run |  |  | Claude (QA) | 2026-09-27
F6 | F. Calendar | Bulk delete mix | Skips published | P1 | Blocked |  |  | Claude (QA) | 2026-09-27
F7 | F. Calendar | Slots and queues | Next slots | P2 | Not run | Pages load (200). |  | Claude (QA) | 2026-09-27
F8 | F. Calendar | Queue/Drafts/Approvals/Sent tabs | Right posts | P1 | Fail | With no channel connected every tab shows the same 'Welcome — Connect a channel' empty state, so Drafts cannot be reached from Publish. | BUG-20 | Claude (QA) | 2026-09-27
G1 | G. Approvals/portal | Contributor submits (internal) | Pending review | P0 | Blocked | Needs a contributor user (SMTP). |  | Claude (QA) | 2026-09-27
G2 | G. Approvals/portal | Manager approve/changes/reject | Status + notify | P0 | Blocked |  |  | Claude (QA) | 2026-09-27
G3 | G. Approvals/portal | Client magic-link email | Opens portal | P0 | Blocked | No SMTP. | BUG-02 | Claude (QA) | 2026-09-27
G4 | G. Approvals/portal | Client approve/reject/hold | Held doesn't publish | P0 | Blocked |  |  | Claude (QA) | 2026-09-27
G5 | G. Approvals/portal | Expired/reused magic link | Expired page | P1 | Pass | /portal/ without a token redirects to a 'This link has expired' page with no access. Copy is misleading when there was never a link. | BUG-24 | Claude (QA) | 2026-09-27
G6 | G. Approvals/portal | Comments own vs others | Others blocked | P1 | Blocked |  |  | Claude (QA) | 2026-09-27
G7 | G. Approvals/portal | Version diff | Shows diff | P2 | Blocked |  |  | Claude (QA) | 2026-09-27
G8 | G. Approvals/portal | Reminder email once | Once | P2 | Blocked |  |  | Claude (QA) | 2026-09-27
G9 | G. Approvals/portal | Portal pages scoped to client | Scoped | P1 | Blocked |  |  | Claude (QA) | 2026-09-27
H1 | H. CSV import | Editor imports 20-row CSV | Preview then import | P1 | Fail | 'Validate & Preview' returns Server Error (500) even for a clean 1-row CSV. Log: AttributeError: type object 'SocialAccount' has no attribute 'Platform' (apps/composer/views.py line 3434, csv_preview). | BUG-16 | Claude (QA) | 2026-09-27
H2 | H. CSV import | Contributor import -> Pending review | Pending | P0 | Blocked | Blocked by H1. | BUG-16 | Claude (QA) | 2026-09-27
H3 | H. CSV import | Bad file -> row-level errors | Row errors | P1 | Fail | 500 instead of row errors. | BUG-16 | Claude (QA) | 2026-09-27
I1 | I. Media library | Upload, folders, move, delete; persists after redeploy | Persists (S3) | P0 | Fail | Upload, reload and delete work. Storage is local disk (see PRE-4). Folders/move not tested. | BUG-03 | Claude (QA) | 2026-09-27
I2 | I. Media library | Video thumbnail | Thumbnail | P2 | Fail | Existing MP4 shows a grey play icon, no thumbnail; the detail-panel player stays at 0:00 and never loads. | BUG-21 | Claude (QA) | 2026-09-27
I3 | I. Media library | Storage quota message | Clear | P2 | Not run |  |  | Claude (QA) | 2026-09-27
J1 | J. Beta features | Inbox shows comments | Shown | P2 | Blocked |  |  | Claude (QA) | 2026-09-27
J2 | J. Beta features | Inbox reply/notes/assign | Saved | P2 | Blocked |  |  | Claude (QA) | 2026-09-27
J3 | J. Beta features | Analytics numbers; no crash on empty | No crash | P2 | Pass | Empty state renders without error (no accounts). |  | Claude (QA) | 2026-09-27
J4 | J. Beta features | Bell unread count polls | Updates | P1 | Not run |  |  | Claude (QA) | 2026-09-27
J5 | J. Beta features | Failed publish notifies owner | In-app + email | P0 | Blocked | No SMTP, no accounts. | BUG-02 | Claude (QA) | 2026-09-27
K1 | K. Permissions | Viewer writes all 403 | 403 | P0 | Blocked | Needs role users (SMTP). |  | Claude (QA) | 2026-09-27
K2 | K. Permissions | Contributor cannot publish directly | Pending review | P0 | Blocked |  |  | Claude (QA) | 2026-09-27
K3 | K. Permissions | Editor cannot manage members/billing | Blocked | P0 | Blocked |  |  | Claude (QA) | 2026-09-27
K4 | K. Permissions | Client blocked from internal pages | Blocked | P0 | Blocked |  |  | Claude (QA) | 2026-09-27
K5 | K. Permissions | Removed member old tab | Redirect login | P0 | Blocked |  |  | Claude (QA) | 2026-09-27
L1 | L. Tenant isolation | Org B opens Org A URLs | 403/404 | P0 | Fail | All 15 Org A workspace pages returned 403 to an outsider account (good). BUT Org A's media file /media/media_library/2026/09/vasavi-atlantis-meta-9x16.mp4 downloads for the outsider AND for a logged-out browser. Any unpublished client asset is public to anyone who has or guesses the URL. | BUG-17 | Claude (QA) | 2026-09-27
L2 | L. Tenant isolation | Org B writes to Org A by changing IDs | Refused | P0 | Pass | Media upload and compose save into Org A's workspace from Org B returned 403. |  | Claude (QA) | 2026-09-27
L3 | L. Tenant isolation | Org A magic link while logged in as Org B | Scoped | P0 | Blocked | No SMTP. |  | Claude (QA) | 2026-09-27
L4 | L. Tenant isolation | Org A API key on Org B | Refused | P0 | Not run |  |  | Claude (QA) | 2026-09-27
L5 | L. Tenant isolation | Search/notifications/exports scoped | Scoped | P0 | Not run |  |  | Claude (QA) | 2026-09-27
M1 | M. Security | XSS strings everywhere | Plain text | P0 | Partial | Escaped in idea title/body, composer caption and CSV preview table. Emails, portal, workspace/display names not tested. |  | Claude (QA) | 2026-09-27
M2 | M. Security | SSRF link preview | Refused | P0 | Not run |  |  | Claude (QA) | 2026-09-27
M3 | M. Security | Webhooks secret + rate limit | Rejected / 429 | P0 | Not run | WEBHOOK_SECRET not set (PRE-6). | BUG-04 | Claude (QA) | 2026-09-27
M4 | M. Security | No default superuser; admin throttled | Throttled | P0 | Fail | Django admin login is public at /admin/ and the pre-deploy command re-creates a superuser from env vars on every deploy (known hole). Brute force not attempted. | BUG-07 | Claude (QA) | 2026-09-27
M5 | M. Security | HTTPS, cookie flags, no stack traces | Clean | P0 | Pass | HSTS, CSP, X-Frame-Options, nosniff, Referrer-Policy, COOP present; session cookie not readable by JS; 500s show a toast, no trace. Permissions-Policy header missing (minor). |  | Claude (QA) | 2026-09-27
M6 | M. Security | SVG with script / HTML as .png | Rejected | P0 | Pass | Both rejected server-side (UX issue in BUG-15). |  | Claude (QA) | 2026-09-27
M7 | M. Security | CSRF from another site | Rejected | P0 | Not run |  |  | Claude (QA) | 2026-09-27
N1 | N. Publisher | 20 posts over 2 h, >=99% on time | 99% | P0 | Blocked | No accounts; worker command wrong. | BUG-06 | Claude (QA) | 2026-09-27
N2 | N. Publisher | 5 posts same minute | All once | P0 | Blocked |  |  | Claude (QA) | 2026-09-27
N3 | N. Publisher | Worker restart | Exactly once | P0 | Blocked |  |  | Claude (QA) | 2026-09-27
N4 | N. Publisher | Worker down 15 min | Publish or marked missed | P1 | Blocked |  |  | Claude (QA) | 2026-09-27
N5 | N. Publisher | Temporary error retries | Backoff | P1 | Blocked |  |  | Claude (QA) | 2026-09-27
N6 | N. Publisher | Permanent error | Fails once | P0 | Blocked |  |  | Claude (QA) | 2026-09-27
N7 | N. Publisher | One platform fails | Others publish | P1 | Blocked |  |  | Claude (QA) | 2026-09-27
N8 | N. Publisher | First comment | Posted | P2 | Blocked |  |  | Claude (QA) | 2026-09-27
O1 | O. Ops | Deploy while users work | No loss | P1 | Not run |  |  | Claude (QA) | 2026-09-27
O2 | O. Ops | Restore DB backup | Row counts match | P0 | Not run | No evidence of a backup. |  | Claude (QA) | 2026-09-27
O3 | O. Ops | Media after 2 redeploys | Loads | P0 | Fail | Local disk, no volume: guaranteed loss on redeploy (by configuration). | BUG-03 | Claude (QA) | 2026-09-27
O4 | O. Ops | /health/ with DB down | Non-200 | P2 | Not run |  |  | Claude (QA) | 2026-09-27
O5 | O. Ops | Sentry from web + worker | Both | P1 | Fail | Not configured. Also every Railway log line (even 404 warnings) is tagged severity 'error', which buries real errors. | BUG-04 | Claude (QA) | 2026-09-27
O6 | O. Ops | All transactional emails | Arrive, branded | P1 | Blocked | No SMTP. | BUG-02 | Claude (QA) | 2026-09-27
P1 | P. Accessibility | Keyboard-only core flow | Visible focus | P1 | Partial | Login: all controls reachable, focus visible. App flow not completed (no accounts). |  | Claude (QA) | 2026-09-27
P2 | P. Accessibility | Modal focus trap + Esc | Trapped, returns | P1 | Fail | Create Idea modal: focus stays on the trigger, Tab moves to the page behind, no role='dialog'/aria-modal. Esc does close it. | BUG-18 | Claude (QA) | 2026-09-27
P3 | P. Accessibility | Screen reader | Announced | P2 | Not run |  |  | Claude (QA) | 2026-09-27
P4 | P. Accessibility | Contrast on primary buttons/body | No failures | P2 | Fail | White on olive 'Sign In' button 2.7:1; white on orange #F97316 buttons 2.8:1; orange links 2.7-2.8:1; 'SM BEAN · STUDIO' eyebrow 2.7:1; 'OR' divider 2.5:1. WCAG AA needs 4.5:1. | BUG-19 | Claude (QA) | 2026-09-27
P5 | P. Accessibility | Zoom 200% | No overlap | P2 | Not run |  |  | Claude (QA) | 2026-09-27
Q1 | Q. Mobile | Smoke on iPhone/Android | Works | P1 | Partial | Login and portal-expired pages fit at 375 px. App shell not tested on mobile. |  | Claude (QA) | 2026-09-27
Q2 | Q. Mobile | Calendar on phone | Usable | P1 | Not run |  |  | Claude (QA) | 2026-09-27
Q3 | Q. Mobile | Upload from camera roll | Works | P1 | Not run |  |  | Claude (QA) | 2026-09-27
Q4 | Q. Mobile | Chrome/Safari/Firefox/Edge | Same | P1 | Not run | Chrome only this round. |  | Claude (QA) | 2026-09-27
R1 | R. Public pages | Landing/pricing claims true | True | P1 | Fail | /pricing/ 404. Signup subtitle promises 'approvals across 10+ platforms' — only Bluesky, Mastodon and DEV.to are usable by beta users today. | BUG-22 | Claude (QA) | 2026-09-27
R2 | R. Public pages | Terms/Privacy/Support links | Real pages | P0 | Fail | /terms/ /privacy/ /support/ 404. Signup 'Terms of Service' and 'Privacy Policy' link to brightbean.xyz — another product's legal pages. | BUG-08 | Claude (QA) | 2026-09-27
R3 | R. Public pages | Brand sweep, no BrightBean | SM Bean only | P2 | Fail | Login/signup logo is 'brightbean-studio-logo.webp' (mascot badge reads 'STUDIO'); eyebrow 'SM BEAN · STUDIO'; legal links to brightbean.xyz. | BUG-23 | Claude (QA) | 2026-09-27
R4 | R. Public pages | Branded 404/403 | Branded | P2 | Fail | 404 is a raw serif 'Not Found' page; 403 is a 135-byte plain response. No way back home. | BUG-24 | Claude (QA) | 2026-09-27
R5 | R. Public pages | robots.txt, titles | Present | P2 | Fail | robots.txt 404; no meta robots; several pages titled just 'SM Bean' (Workspaces, Notifications, Social accounts, Ideas, Publish queue). | BUG-25 | Claude (QA) | 2026-09-27
S1 | S. Performance | Main pages < 2 s | < 2 s | P2 | Pass | Server responses 0.3-0.65 s (empty workspace). Retest with 200 posts/files. |  | Claude (QA) | 2026-09-27
S2 | S. Performance | 50 MB video upload | Completes | P2 | Not run |  |  | Claude (QA) | 2026-09-27
S3 | S. Performance | Loading indicators, no double submit | Shown | P1 | Not run |  |  | Claude (QA) | 2026-09-27

## Bugs
Bug ID | Severity | Area | Title | Steps to reproduce | Expected | Actual | Evidence | Suggested fix | Status | Linked tests | Owner | Target date | Engineering response (27 Sep)
BUG-01 | P0 | Release | Production is still running pre-PR-#1 code | Check Railway deployments for sm-bean and sm-bean-worker | PR #1 deployed | Last deploy 24 Sep, commit 566b08c. Every PR #1 fix (terms, pricing, logout POST, robots) is missing | Railway deployments list; /terms/ 404 | Take a DB backup, merge PR #1, redeploy both services, re-run smoke | Open | PRE-1 | Eng / Hemant |  | Release branch claude/loving-euler-x05qbg = PR #1 + all round-1 fixes (2,357 tests green). Deploy = backup DB, merge, switch worker to run_worker, redeploy both. See docs/audit/QA_ROUND1_RESPONSE.md runbook.
BUG-02 | P0 | Email | No SMTP configured: no email can be sent | Railway > sm-bean > Variables | EMAIL_HOST etc. set | No email variables. Invites, password reset, magic links, approval requests, failure alerts all dead | Variable list | Add a transactional provider (Postmark/SES/Resend), set vars, verify SPF/DKIM/DMARC on the sending domain | Open | PRE-3, SMK-4, SMK-5, SMK-9, A3, A7, C2, G3, J5, O6 | Hemant |  | Code ready (EMAIL_HOST/PORT/USER/PASSWORD, DEFAULT_FROM_EMAIL). Needs a provider account (Resend/Postmark/SES) + SPF/DKIM/DMARC on the sending domain. Deploy check smbean.W004 flags it.
BUG-03 | P0 | Storage | Media stored on container disk, not S3 | Upload an image; inspect URL | S3/R2 URL, persists across deploys | Served from /media/media_library/YYYY/MM/<file> on the web container; no volume, no S3 vars | Network tab; Railway config | Configure django-storages with S3/R2 (private bucket, signed URLs), migrate existing files | Open | PRE-4, SMK-6, I1, O3 | Eng |  | S3/R2 backend already in code (STORAGE_BACKEND=s3 + S3_*; private ACL, 1-h signed URLs). Create a Railway bucket or R2 bucket at cutover and set the vars; copy the few existing files.
BUG-04 | P1 | Ops | Sentry, SUPPORT_EMAIL, WEBHOOK_SECRET missing; all logs tagged 'error' | Railway variables and logs | Set; correct log levels | Not set; 404 warnings appear as severity error | Railway logs | Set vars; route INFO/WARNING to stdout at correct level (JSON logging) | Partly fixed | PRE-5, PRE-6, SMK-12, M3, O5 | Eng / Hemant |  | JSON logs on stdout with real levels; gunicorn lines to stdout; Sentry env/release. WEBHOOK_SECRET set on Railway 27 Sep. Still needs SENTRY_DSN (web + worker) and SUPPORT_EMAIL from owner.
BUG-05 | P0 | Auth | Anyone can sign up with any email (invite-only not enforced) | Logged out, open /accounts/signup/, submit any email + password | 'Signup is invite only' page, no account | Account and workspace created immediately; no invite, no email verification | Created qa-test-noninvited@example.com during test (please delete) | Set SIGNUP_MODE=invite_only + SIGNUP_ALLOWLIST; enforce in allauth adapter for email and Google paths; require email verification | Fixed – retest after deploy | PRE-7, SMK-3, A2 | Eng |  | Invite-only enforced for email and Google signup (SIGNUP_MODE=invite_only now set on Railway); invite links now admit only the invited address. Turn on ACCOUNT_EMAIL_VERIFICATION=mandatory once SMTP works. Please delete qa-test-noninvited@example.com.
BUG-06 | P0 | Publisher | Worker runs the wrong command | Railway > sm-bean-worker > Start command | run_worker | python manage.py process_tasks | Service config | Set start command to run_worker after PR #1; restart after migrations | Open | PRE-8, SMK-10, N1 | Eng |  | run_worker ships with the release; set worker start command to 'python manage.py run_worker' in the same deploy (it does not exist on the current prod code).
BUG-07 | P0 | Security | Pre-deploy re-creates superuser and resets its password on every deploy | Railway > sm-bean > pre-deploy command | No superuser bootstrap in prod | DJANGO_SUPERUSER_EMAIL/PASSWORD set; shell snippet sets password every deploy; /admin/ publicly reachable | Service config | Remove the snippet and vars, rotate the admin password, restrict /admin/ (IP allowlist or 2FA) and throttle it | Open | PRE-9, M4 | Eng / Hemant |  | Railway pre-deploy changed 27 Sep to 'python manage.py migrate --noinput' (no more password reset). New ADMIN_URL + ADMIN_ALLOWED_IPS; admin login throttled. Owner: delete DJANGO_SUPERUSER_* vars and rotate the admin password.
BUG-08 | P0 | Legal | Terms and Privacy missing; signup links to another company's legal pages | Open /terms/, /privacy/; check signup footer links | Own legal pages | 404; signup links to brightbean.xyz/terms-of-service and /privacy-policy | Page source of /accounts/signup/ | Publish real Terms/Privacy (DPDP + GDPR basics, Meta/Google data-use wording needed for app review) and relink | Fixed – retest after deploy | PRE-11, R2 | Eng / Legal |  | /terms/, /privacy/ (DPDP + GDPR, Google Limited Use, Meta Platform Terms) and new /support/. Shown as 'Draft' until LEGAL_PAGES_REVIEWED=true after counsel review; set LEGAL_ENTITY_NAME.
BUG-09 | P0 | QA setup | No test social accounts connected | Open Social accounts | Bluesky, Mastodon, DEV.to + Meta/YouTube tester accounts | 0 accounts | Connect page | Create and connect dedicated test accounts before the next round | Open | PRE-12, SMK-7, SMK-8, D1 | Hemant |  | Create and connect Bluesky, Mastodon, DEV.to test accounts (+ Meta/YouTube tester accounts) before round 2.
BUG-10 | P1 | Auth | Logout works over GET; logout is a link | Visit /accounts/logout/ in any tab or via an <img> on another site | Confirmation page / POST button | User is signed out silently | Reproduced in Chrome and in-app browser | ACCOUNT_LOGOUT_ON_GET=False; turn sidebar item into a POST form button | Fixed – retest after deploy | A9, A10 | Eng |  | Logout is POST-only (GET returns 405, verified in Chrome); sidebar uses a POST button.
BUG-11 | P1 | Onboarding | No onboarding checklist for new users | Sign up; land in app | 4-step checklist | Straight to Publish with a generic empty state | Screenshot 01 | Build the checklist card on first run (connect, post, idea, invite) with progress | Fixed – retest after deploy | B1 | Eng |  | 4-step Get started checklist with progress, minimise and dismiss (verified in Chrome).
BUG-12 | P1 | Social | Sidebar promotes platforms that cannot be connected | Look at sidebar 'CONNECT CHANNELS' | Only ready platforms | 'LinkedIn (Company Page)' and 'TikTok' shown as first suggestions | Screenshot 01 | Drive the sidebar list from configured platforms; label others 'Coming soon' | Fixed – retest after deploy | D7 | Eng |  | Sidebar lists only connectable platforms; unavailable ones say 'Coming soon' for everyone.
BUG-13 | P0 | Composer | Save Draft with no account silently discards the post | Compose > type caption > Save Draft (no channel selected) | Draft saved, or clear error | 204, redirect to Publish, no message, '0 drafts' | Network: POST compose/save/ 204 | Allow account-less drafts (drafts should not need a channel) or block with inline error; never 204 on a no-op | Fixed – retest after deploy | E1, E14 | Eng |  | Save Draft with no channel saves, shows 'Draft saved', stays on the post (verified in Chrome); channel-less drafts appear in Publish > Drafts and its badge.
BUG-14 | P1 | Composer | Idea 'Create Post' makes an invisible ghost post and drops the title | Idea > Create Post | Draft visible in Drafts, title kept | Post record exists only by URL; Drafts shows 0; title lost | Post 5265c8a5… (deleted after test) | Include account-less posts in Drafts; map idea title into caption or post title | Fixed – retest after deploy | E4, E16 | Eng |  | Idea > Create Post keeps the title (shown in drafts; seeds an empty caption) and the post is visible in Drafts.
BUG-15 | P1 | Media | Rejected uploads fail silently | Upload a text file renamed .jpg | Inline error naming the reason | HTTP 200 empty body, page reloads, file gone | Network | Return 400 with per-file errors and show them in the uploader | Fixed – retest after deploy | E8 | Eng |  | Uploads answer 400 with a per-file reason shown inline (verified in Chrome). Also closed: composer/idea uploads skipped type checks (stored-XSS risk).
BUG-16 | P1 | CSV import | CSV preview crashes (500) on every file | Import CSV > Upload > Validate & Preview | Preview with row errors | Server Error (500): AttributeError SocialAccount.Platform (views.py:3434) | Railway logs 06:21 and 06:22 UTC | Use the correct platform enum (e.g. SocialAccount.platform choices / Platform model); add a unit test for csv_preview | Fixed – retest after deploy | H1, H2, H3 | Eng |  | Wrong enum fixed; row-level errors render. Regression tests added.
BUG-17 | P0 | Security | Media files are public to anyone with the URL (cross-tenant) | Log out (or log in as Org B), open /media/media_library/2026/09/<file> | 403 / signed URL | File downloads (200/206) | Tested logged-out and as outsider | Private bucket + short-lived signed URLs, or an auth-checked media view; random (UUID) filenames | Open | L1 | Eng |  | New uploads get random 128-bit filenames; Caddy limited to public prefixes. Full fix = private S3 bucket with signed URLs at cutover (BUG-03).
BUG-18 | P1 | Accessibility | Modals do not manage focus | Create Idea > press Tab | Focus inside dialog, trapped | Focus stays on trigger; Tab reaches page behind; no dialog role | Keyboard test | Use a dialog primitive (native <dialog> or focus-trap), role=dialog, aria-modal, return focus | Fixed – retest after deploy | P2 | Eng |  | Dialogs use role=dialog, aria-modal, x-trap focus trap, Esc, focus return.
BUG-19 | P2 | Design | Brand colours fail contrast | Measure primary buttons/links | ≥4.5:1 | 2.5-2.8:1 | Contrast script | Darken brand orange to ~#C2410C and olive to ~#5F6B1F for text/buttons; keep bright tints for fills | Fixed – retest after deploy | P4 | Eng |  | --primary is #C2410C (5.2:1); orange text/buttons moved to 700/800; olive removed.
BUG-20 | P2 | Publish | Empty state hijacks Publish tabs and Calendar toggle | No channel connected; click Drafts, then Calendar | Show drafts; switch view | Every tab shows 'Welcome'; first Calendar click ignored | Screenshot 03 | Show empty state as a banner, keep tabs functional | Fixed – retest after deploy | F1, F8 | Eng |  | One slim 'connect a channel' banner; tabs keep their own content. Calendar toggle worked on first click in Chrome retest; Back/Forward partial bug also fixed.
BUG-21 | P2 | Media | Video has no thumbnail and preview player never loads | Media > open MP4 | Thumbnail + playable | Grey icon; player stuck at 0:00 | Screenshot 05 | Generate poster frame on upload; serve with Range support | Fixed – retest after deploy | I2 | Eng |  | Poster frame + Range-capable stream for the player; composer/idea uploads now queue thumbnail generation (worker must be on run_worker).
BUG-22 | P1 | Content | Signup copy over-promises platforms; pricing page missing | Open signup, /pricing/ | Accurate claims | '10+ platforms'; /pricing/ 404 | Screenshot 02 | Say 'Bluesky, Mastodon and DEV.to today; Meta and YouTube coming soon' | Fixed – retest after deploy | R1 | Eng |  | Copy lists live platforms from LAUNCHED_PLATFORMS (Bluesky, Mastodon, DEV.to) and the rest as coming soon; /pricing/ live.
BUG-23 | P2 | Brand | BrightBean leftovers | Login/signup | SM Bean brand only | BrightBean Studio mascot logo ('STUDIO' badge), 'SM BEAN · STUDIO' | Screenshot 02 | Replace logo and eyebrow; grep templates/static for 'brightbean' | Fixed – retest after deploy | R3 | Eng |  | Mascot/STUDIO/brightbean.xyz removed from login, signup, legal. (Held back PR #2 marketing site: it reintroduces them.)
BUG-24 | P2 | Errors | Unbranded 404/403 and misleading portal 'expired' page | Open a bad URL; open /portal/ with no link | Branded pages with a way home | Raw 'Not Found'; 403 plain text; portal says link 'expired' though none was used | Screenshot 04 | Add 404.html/403.html/500.html in the app shell; separate 'invalid link' vs 'expired link' copy | Fixed – retest after deploy | G5, R4 | Eng |  | Branded 400/403/404/500; portal distinguishes no link / invalid / used / expired, with 'Request a new link'.
BUG-25 | P2 | SEO/meta | No robots.txt, missing page titles | Open /robots.txt; check <title> | robots.txt disallows app; unique titles | 404; 6 pages titled 'SM Bean' | Crawl table | Add robots.txt and noindex on app pages; set titles per page with one separator style | Fixed – retest after deploy | R5 | Eng |  | robots.txt + sitemap; every page has 'Page · SM Bean' title.
BUG-26 | P3 | QA plan | Plan links point at internal endpoints | Open /workspace/{ws}/tags/ and /ideas/board/ | Pages | Raw JSON '[]' and an unstyled HTMX fragment | Screenshots | Update plan: Ideas is /workspace/{ws}/create/; tags are managed inside composer | Plan update | E11 | QA |  | Ideas live at /workspace/{ws}/create/; tags are managed in the composer (/tags/ is an internal JSON endpoint).
BUG-27 | P3 | Copy | Timezone shown as 'Calcutta'; media times in UTC | Publish filter; Media detail | 'Kolkata'; workspace time | 'Calcutta (workspace)'; upload time 6:19 AM (UTC) for an 11:49 AM IST upload | Screenshot 05 | Use current IANA names in labels; render all times in workspace tz | Fixed – retest after deploy | C6 | Eng |  | Asia/Calcutta etc. stored/shown as current names (data migration for existing rows); media times in workspace tz.
BUG-28 | P2 | Layout | Media library layout defects | Open Media library | Clean layout | 'FOLDERS' heading clipped to 'OLDERS'; Upload button clipped; new upload renders as a full-width giant card until reload; detail drawer overflows off-screen (close X and Delete cut) | Screenshots 05-06 | Fix container padding/overflow; constrain new card to grid; drawer max-width: 100vw | Fixed – retest after deploy |  | Eng |  | Header/Upload no longer clipped; polling card never replaced by JSON; drawer fits the viewport (verified desktop + 375 px).
BUG-29 | P3 | Navigation | Wrong active nav item on composer; stray scroll arrows beside Publish tabs | Open composer; look at Publish tabs | Correct highlight; no widget | 'Create Idea' highlighted on New Post; tiny up/down scroll control beside 'Sent' | Screenshot 01/03 | Fix active-route matching; hide tab-row overflow scrollbar | Fixed – retest after deploy |  | Eng |  | Correct active nav item; tab-row scrollbar hidden.
BUG-30 | P2 | Design | Inconsistent visual language | Compare login, reset, app, analytics, portal | One system | Olive primary on login, orange on reset/app; serif headings on Analytics/portal vs sans elsewhere; three different button styles for primary actions | Screenshots | Define tokens (one primary, one type family, 3 button variants) and apply | Partly fixed |  | Eng / Design |  | One primary colour and button palette; serif display headings on Analytics/portal and a real SM Bean wordmark still need a design pass.

## Design & UX
# | Area | What we saw | Why it matters | Recommendation | Priority
1 | Brand colour | Two competing primaries: olive green (#93A240) on login/signup, orange (#F97316) everywhere else, including the password-reset page. | Feels like two products; weak recognition. | Pick one primary (keep orange, it owns the app). Use a darker text-safe shade (#C2410C) for text/buttons and the bright orange only for fills and highlights. | High
2 | Contrast | Primary buttons and links sit at 2.5-2.8:1. | Fails WCAG AA; hard to read on phones outdoors — exactly where clients approve posts. | Darken button backgrounds or switch button text to near-black on light orange. Target ≥4.5:1 for text. | High
3 | Logo & identity | Login uses the BrightBean Studio mascot (reads 'STUDIO'); eyebrow 'SM BEAN · STUDIO'. App sidebar shows a plain orange 'M' tile. | Agencies will notice it is a rebadged product; trust drops. | Commission a simple SM Bean wordmark + bean icon; use it on login, sidebar, favicon, emails and portal. | High
4 | Typography | System UI font in the app; serif display font on Analytics and the portal 'expired' card; raw Times-style 404. | Inconsistent tone. | One family (e.g. Inter or Geist) with a 5-step type scale; optional single display face for H1 only. | Medium
5 | First-run experience | New user lands on 'Publish' with a generic 'Welcome' illustration; tabs and Calendar are effectively locked; no checklist. | Day-one agency cannot tell what to do first; high drop-off risk. | Guided checklist card (Connect → Create post → Invite client → Schedule), progress bar, and a sample 'demo' post so the calendar is never empty. | High
6 | Empty & error states | Silent failures (draft save, rejected upload), raw 404/403, 500 as a tiny toast. | Users lose work without knowing; support load. | Every write returns a visible result: success toast, inline field error, or a full-page branded error with a next step. | High
7 | Navigation | Sidebar mixes actions ('New', 'Create Idea') with places; 'Connect channels' suggests unavailable platforms; wrong active item on composer. | Orientation cost. | Group as Plan (Calendar, Ideas) · Engage (Inbox) · Measure (Analytics) · Settings. Move 'Connect channels' into a dismissible setup card. | Medium
8 | Composer | Clean two-pane layout with preview (good). But no account picker visible when none connected, only grey 'No accounts connected'. | Primary task blocked with no guidance. | Show an account picker row always; when empty, a clear 'Connect your first channel' button inline. Keep Save Draft always available. | High
9 | Calendar | Past days rendered in heavy grey, today in orange; legend is clear. | Past-day grey is heavy and lowers legibility of past posts. | Lighter past-day tint; show post chips with platform icons and status colour; sticky week header. | Low
10 | Media library | Clipped header/upload button, giant card after upload, drawer overflowing viewport, no video thumbnails. | Looks unfinished. | Fix grid & drawer sizing, generate thumbnails, add upload progress list. | Medium
11 | Client portal | Clean, calm card. Copy says 'expired' for any invalid link. | Clients may think they missed a deadline. | Split 'invalid' vs 'expired'; add agency logo and a 'Request a new link' button that notifies the team. | Medium
12 | Accessibility | Visible focus on login (good); modals don't trap focus; no dialog roles. | Keyboard and screen-reader users get lost. | Adopt one accessible dialog component; run axe in CI. | Medium
13 | Microcopy | 'Not Configured' (developer wording); 'Calcutta'; '10+ platforms'. | Confusing / over-promising. | 'Coming soon', 'Kolkata', and an honest platform list. | Low
Proposed colour tokens
| primary-600 (buttons, links) | #C2410C | White text 5.2:1
| primary-500 (fills, highlights) | #F97316 | Use behind dark text only
| primary-50 (tints) | #FFF7ED | Backgrounds, selected rows
| ink-900 (body text) | #1C1917 | 17:1 on white
| ink-500 (secondary text) | #57534E | 7.3:1 on #FAFAF9
| success | #15803D | Published
| danger | #B91C1C | Failed / delete

## Exit Criteria
Exit criterion | Met? | Evidence
All pre-conditions ticked | No | 10 of 12 failed — see PRE-1…PRE-12
P0 smoke passed twice on two deploys | No | SMK-3, SMK-6 failed; 7 steps blocked
Zero open P0 and P1 bugs | No | See Summary
Sections K, L, M all passed | No | L1 and M4 failed; K blocked
Publish success ≥99% (N1), zero duplicates | No | Blocked
Worker restart test N3 passed 3× | No | Blocked
DB restore O2 proven | No | Not run
Transactional emails arrive, not spam | No | No SMTP
P2 bugs have owner and date | No | Owner/Target columns empty on Bugs tab
Beta testers told which platforms work | No | Signup still says 10+ platforms